## RPA RoadMap (2) (hidden)
Sr# | UseCase Name | Average Transactions (Annual) | OCR / NON-OCR | Already in production | Automation Required | RPA Complexity | Estimated Efforts(Weeks) | Developer | Timeline
1 | Data Change – Override Manager | 6089 | NON-OCR | Y | Y | Medium |  | Varun
2 | Data Change – Use Position Reports To | 3933 | NON-OCR | Y | Y | Simple |  | Varun
3 | Job Architecture | 10692 | NON-OCR | Y | Y | Medium |  | Varun
4 | Job Description Update | 7168 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Mar-April
5 | Data Change – Override Person Job Band | 4 | NON-OCR |  | N
6 | Data Change – Use Position Job Band | 7 | NON-OCR |  | N
7 | Data Change – Data Change | 6804 | NON-OCR | N | Y | Medium | 5.8 | Kishor | May
8 | External Hire Poornata ID creation | 5170 | NON-OCR | N | Y | Complex | 8.6 | Kishor | June- July
9 | Poornata ID creation (Add a Person - Smart HR) | 1057 | NON-OCR |  | N | Medium
10 | Poornata ID Creation (Add a Person) - Excel Template | 5159 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Aug-Sep
11 | Poornata ID Creation (Add POI/CWR) | 573 | NON-OCR |  | N | Complex
12 | Job Data Update (Confirmation/Confirmation with pay rate change/Mobility) | 10119 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | Nov-Dec-Jan-Feb
13 | Personal Data Update (Excluding Bulk volume-43,274) | 14504 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | Nov-Dec-Jan-Feb
14 | Compensation Update (Excluding bulk volume-71,968) | 7232 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | Nov-Dec-Jan-Feb
15 | Creation of Potential Assessment Document | 5337 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Oct-Nov 2024
16 | Poornata ID Creation (Add a Person) (Proposed Process Change) | 8925 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | Aug-Sep-Oct
17 | Bank Data Update | 3695 | OCR | N | Y | Medium | 8.8 | Rutuja , Vibhav | April - May-June-July
18 | Poornata ID creation (Through External Hire) – QC action and update if missing data-Proposed process change | 5854 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | Aug-Sep-Oct
19 | Education Data | 2981 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | April - May-June-July
20 | National ID, PAN, Aadhar, Passport, Visa, Address | 9845 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | April - May-June-July
21 | Learning Session creation | 1277 | NON-OCR |  | N
22 | Leave Balance upload | 4243 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Dec-Jan
23 | BGV initiation and Report upload Initiate – 20 mins Report upload 10 mins | 5228 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Feb-Mar 2025
24 | FnF Settlement | 12829 | NON-OCR | N | Y | Complex | 8.6 | Ganesh / Tushar | April - May
25 | Maker-Checker - ACR Letter |  | NON-OCR | N | Y | Complex | 8.6 | Ganesh / Tushar | June- July -Aug
26 | Ticket Creater | 48701 | NON-OCR | Y | Y | Complex |  | Varun
27 | Talent Profile Creation BOT | 5310 | NON-OCR | Y | Y | Complex |  | Varun
28 | Poornata Status update - SR Update in Transaction | 53182 | NON-OCR | Y | Y | Simple |  | Viji
29 | Audit Sampling |  | NON-OCR | Y | Y | Simple |  | Viji
30 | Create a Dashboard |  | NON-OCR | Y | Y | Simple |  | Viji
31 | Cement ticket creator |  | NON-OCR | Y | Y | Complex |  | Viji
32 | Potential Assesment | 6316 | NON-OCR | Y | Y | Medium |  | Viji
33 | PH Link Initiation (ABCAP) | 111114 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | Aug-Sep-Oct
34 | Cancelling of performance document | 1639 | NON-OCR | N | Y | Medium | 5.8 | Kishor | April-May 2025
35 | Creation and Assigning of Curriculum/ Deeplinks/ Online Courses/ Uploading Videos | 2025 | NON-OCR | N | Y | Medium | 5.8 | Kishor | June-July 2025
36 | Creation of performance document | 2013 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Aug-Sep 2025
37 | Exit_Approval reassignment for Clearance | 1931 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Oct-Nov 2025
38 | Holiday Schedule upload | 10287 | NON-OCR | N | Y | Simple | 4.8 | Kishor | 2025-12-01
39 | Incident Class. / Data / sync issue | 1926 | NON-OCR | N | Y | Medium | 5.8 | Kishor | Jan - Feb 2026
40 | JD linkage | 4037 | NON-OCR | N | Y | Medium | 5.8 | Kishor | March-April 2026
41 | Job Data Update | 45835 | NON-OCR | N | Y | Medium | 5.8
42 | Job Data Update (Resignation, Separation and Transfer) | 4381 | NON-OCR | N | Y | Medium | 5.8
43 | Mobility_HR Initiated Transfer | 7125 | NON-OCR | N | Y | Medium | 5.8
44 | New/ Old Event | 2192 | NON-OCR | N | Y | Complex | 8.6
45 | Onboarding Initiation | 2676 | NON-OCR | N | Y | Complex | 8.6
46 | Position Creation/ Updation/ Deactivation and JD Linkage (Job Arch ???) | 9247 | NON-OCR | N | Y | Medium | 5.8

## RPA RoadMap (3) (hidden)
| RPA Use Cases | [9 empty] | 2024 | [8 empty] | 2025 | [11 empty] | 2026
Sr# | UseCase Name | Average Transactions (Annual) | OCR / NON-OCR | Already in production | Automation Required | RPA Complexity | Estimated Efforts(Weeks) | Developer | Timeline | Smonth | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
4 | Job Description Update | 7168 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Mar-April | 202403 | 1
20 | National ID, PAN, Aadhar, Passport, Visa, Address | 9845 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | April - May-June-July | 202404 | 1 | 1 | 1 | 1
17 | Bank Data Update | 3695 | OCR | N | Y | Medium | 8.8 | Rutuja , Vibhav | April - May-June-July | 202404 | 1 | 1 | 1 | 1
19 | Education Data | 2981 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | April - May-June-July | 202404 | 1 | 1 | 1 | 1
24 | FnF Settlement | 12829 | NON-OCR | N | Y | Complex | 8.6 | Ganesh / Tushar | April - May | 202404 | 1 | 1
38 | Holiday Schedule upload | 10287 | NON-OCR | N | Y | Simple | 4.8 | Kishor | May | 202405 |  | 1
41 | Job Data Update | 45835 | NON-OCR | N | Y | Medium | 5.8 | Kishor | June- July | 202406 |  |  | 1 | 1
25 | Maker-Checker - ACR Letter |  | NON-OCR | N | Y | Complex | 8.6 | Ganesh / Tushar | June- July -Aug | 202406 |  |  | 1 | 1 | 1
33 | PH Link Initiation (ABCAP) | 111114 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | Aug-Sep-Oct | 202408 |  |  |  |  | 1 | 1 | 1
16 | Poornata ID Creation (Add a Person) (Proposed Process Change) | 8925 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | Aug-Sep-Oct | 202408 |  |  |  |  | 1 | 1 | 1
18 | Poornata ID creation (Through External Hire) – QC action and update if missing data-Proposed process change | 5854 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | Aug-Sep-Oct | 202408 |  |  |  |  | 1 | 1 | 1
46 | Position Creation/ Updation/ Deactivation and JD Linkage (Job Arch ???) | 9247 | NON-OCR | N | Y | Medium | 5.8 | Kishor | Aug-Sep | 202408 |  |  |  |  | 1 | 1
15 | Creation of Potential Assessment Document | 5337 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Oct-Nov 2024 | 202410 | [6 empty] | 1 | 1
13 | Personal Data Update (Excluding Bulk volume-43,274) | 14504 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | Nov-Dec-Jan-Feb | 202411 | [7 empty] | 1 | 1 | 1
12 | Job Data Update (Confirmation/Confirmation with pay rate change/Mobility) | 10119 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | Nov-Dec-Jan-Feb | 202411 | [7 empty] | 1 | 1 | 1
14 | Compensation Update (Excluding bulk volume-71,968) | 7232 | OCR | N | Y | Complex | 11.6 | Rutuja , Vibhav | Nov-Dec-Jan-Feb | 202411 | [7 empty] | 1 | 1 | 1
22 | Leave Balance upload | 4243 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Dec-Jan | 202412 | [8 empty] | 1 | 1
23 | BGV initiation and Report upload Initiate – 20 mins Report upload 10 mins | 5228 | NON-OCR | N | Y | Complex | 8.6 | Rutuja | Feb-Mar 2025 | 202502 | [10 empty] | 1 | 1
34 | Cancelling of performance document | 1639 | NON-OCR | N | Y | Medium | 5.8 | Kishor | Feb-Mar 2025 | 202502 | [10 empty] | 1 | 1
35 | Creation and Assigning of Curriculum/ Deeplinks/ Online Courses/ Uploading Videos | 2025 | NON-OCR | N | Y | Medium | 5.8 | Rutuja | Apr-May-25 | 202504 | [12 empty] | 1 | 1
36 | Creation of performance document | 2013 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Apr-May-Jun-25 | 202504 | [12 empty] | 1 | 1 | 1
37 | Exit_Approval reassignment for Clearance | 1931 | NON-OCR | N | Y | Complex | 8.6 | Rutuja | Jun-Jul-Aug-25 | 202506 | [14 empty] | 1 | 1 | 1
7 | Data Change – Data Change | 6804 | NON-OCR | N | Y | Medium | 5.8 | Kishor | 2025-07-01 | 202507 | [15 empty] | 1
40 | JD linkage | 4037 | NON-OCR | N | Y | Medium | 5.8 | Kishor | Aug-Sep-25 | 202508 | [16 empty] | 1 | 1
39 | Incident Class. / Data / sync issue | 1926 | NON-OCR | N | Y | Medium | 5.8 | Rutuja | Sep-Oct-25 | 202509 | [17 empty] | 1 | 1
42 | Job Data Update (Resignation, Separation and Transfer) | 4381 | NON-OCR | N | Y | Medium | 5.8 | Kishor | Oct-Nov-25 | 202510 | [18 empty] | 1 | 1
43 | Mobility_HR Initiated Transfer | 7125 | NON-OCR | N | Y | Medium | 5.8 | Rutuja | Jan-Feb-26 | 202511 | [19 empty] | 1 | 1
8 | External Hire Poornata ID creation | 5170 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Nov-Dec-25 | 202512 | [20 empty] | 1 | 1
10 | Poornata ID Creation (Add a Person) - Excel Template | 5159 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Mar-Apr-26 | 202601 | [21 empty] | 1 | 1 | 1
44 | New/ Old Event | 2192 | NON-OCR | N | Y | Complex | 8.6 | Kishor | Dec-Jan-Feb-26 | 202602 | [22 empty] | 1 | 1
45 | Onboarding Initiation | 2676 | NON-OCR | N | Y | Complex | 8.6 | Rutuja | Mar-Apr-May-26 | 202603 | [23 empty] | 1 | 1 | 1
1 | Data Change – Override Manager | 6089 | NON-OCR | Y | Y | Medium |  | Varun
2 | Data Change – Use Position Reports To | 3933 | NON-OCR | Y | Y | Simple |  | Varun
3 | Job Architecture | 10692 | NON-OCR | Y | Y | Medium |  | Varun
5 | Data Change – Override Person Job Band | 4 | NON-OCR |  | N
6 | Data Change – Use Position Job Band | 7 | NON-OCR |  | N
9 | Poornata ID creation (Add a Person - Smart HR) | 1057 | NON-OCR |  | N | Medium
11 | Poornata ID Creation (Add POI/CWR) | 573 | NON-OCR |  | N | Complex
21 | Learning Session creation | 1277 | NON-OCR |  | N
26 | Ticket Creater | 48701 | NON-OCR | Y | Y | Complex |  | Varun
27 | Talent Profile Creation BOT | 5310 | NON-OCR | Y | Y | Complex |  | Varun
28 | Poornata Status update - SR Update in Transaction | 53182 | NON-OCR | Y | Y | Simple |  | Viji
29 | Audit Sampling |  | NON-OCR | Y | Y | Simple |  | Viji
30 | Create a Dashboard |  | NON-OCR | Y | Y | Simple |  | Viji
31 | Cement ticket creator |  | NON-OCR | Y | Y | Complex |  | Viji
32 | Potential Assesment | 6316 | NON-OCR | Y | Y | Medium |  | Viji

## OverallProcesses (hidden)
Final category | Final catalog | Total
WFA | ABCap Prospective Hire Link Creation | 43
| Bank Data Update | 2876
| Compensation Update | 78207
| Confirmation | 959
| Confirmation with Payrate Change | 1204
| Confirmation with Payrate Change and Promotion | 29
| Data Change - Data Change | 6785
| Data Change - Override Manager | 5918
| Data Change - Override Person Job Band | 16
| Data Change - Use Position Job Band | 10
| Data Change - Use Position Reports To | 3657
| Exit_Approval reassignment for Clearance | 1920
| Exit_Approval reassignment for Resignation | 168
| Exit_Resignation Withdrawal | 18
| Exit_Resignation/Separation/ Termination | 1406
| Holiday Schedule Creation/Updation | 318
| Holiday Schedule upload | 10287
| HR Process (Employee Self Services) / Name Change | 1
| JD linkage | 12
| Job Code Creation | 0
| Job Data Update | 44414
| Job Data Update (Resignation, Separation and Transfer) | 4322
| Leave Balance upload | 2970
| Mobility_Clearance reassignment | 44
| Mobility_HR Initiated Transfer | 7118
| New Leave Configuration | 7
| null | 0
| Personal Data Update | 25248
| Poornata ID creation (Add a Person - Smart HR) | 938
| Poornata ID Creation (Add a Person) | 4101
| Poornata ID Creation (Add POI/CWR) | 507
| Poornata ID creation (Through External Hire) - Business | 4353
| Poornata ID creation (Through External Hire) - SeamEx | 20
| Position Creation/ Updation/ Deactivation | 2396
| Position Creation/ Updation/ Deactivation and JD Linkage | 102
| Position creation/update | 51
| Probation Extension | 33
| Setup /Configuration Changes Required | 822
| WFA (Job data update) | 45
| WFA Others | 191
| Workforce Administration | 31
| Date of Birth Update | 12
| Mobility- Transfers | 2
| Data Change - Full time to Part time | 1
| Changes in Configuration | 2
| Department Creation/Updation | 5
| Changes in Setup | 16
| WFA (Personal data update) | 3
| Service Request Access Required | 2
| Changes in Report | 3
| Cost Centre Creation/Updation | 422
| Admin Access Request | 0
| Personal Data | 1
WFA Total |  | 212016
JAE | ABCap Prospective Hire Link Creation | 36
| Compensation Update | 4
| Confirmation | 921
| Data Change - Data Change | 19
| Data Change - Override Manager | 99
| Data Change - Use Position Reports To | 14
| Incident Class. / Admin / Tech Issues | 1
| JD linkage | 4009
| Job Code Creation | 2
| Job Data Update | 1372
| Job Data Update (Resignation, Separation and Transfer) | 33
| Leave Balance upload | 65
| Mobility_HR Initiated Transfer | 5
| null | 0
| Personal Data Update | 148
| Poornata ID creation (Through External Hire) - SeamEx | 0
| Position Creation/ Updation/ Deactivation | 11041
| Position Creation/ Updation/ Deactivation and JD Linkage | 9145
| Position creation/update | 5097
| Setup /Configuration Changes Required | 8
| Standard Job creation/update | 34
| JAE and Position Management | 16
JAE Total |  | 32069
TM | Business PMS Calendar Update | 0
| Cancellation of Potential Assessment document | 788
| Compensation Update | 0
| Creation of performance document | 20
| Domo Reports Access Request (GVC- Elearning) | 31
| Exit_Resignation/Separation/ Termination | 2
| Incident Class. / Access Issues | 0
| Initiate Background Verification Check | 0
| Initiate EP File Check | 0
| Job Data Update | 0
| Mobility_HR Initiated Transfer | 2
| Personal Data Update | 32
| Process Queries | 0
| Report generation for talent discussions | 6131
| Request for Reports/Data (Other Modules) | 136
| Request for Reports/Data (PMS, Talent and Compensation) | 302
| Setup /Configuration Changes Required | 31
| Talent discussions outcome updation | 869
| Transfer of performance document | 3
| WFA Others | 0
| Succession Planning Updates | 40
| ITM - Transfer Compass Assessment Form ( for more than one employee) | 2
| Creation of Potential Assessment Document | 11157
| Transfer of Potential Assessment document | 361
| Re-opening of Potential Assessment document | 17
| Pre-closure of Potential Assessment Document | 44
| Generate Existing Report | 113
| Any other request | 166
TM Total |  | 20247
TS | ABCap Prospective Hire Link Creation | 2603
| ABMCPL - 1st Day joining forms | 8
| Blacklisting | 7
| Email Notification to Internal B and C category Applicants | 1
| Initiate Background Verification Check | 4427
| Initiate EJF Verification Process | 9840
| Initiate EP File Check | 198
| Initiate Medical Check | 45
| Job Requisition creation and On-boarding | 90
| null | 0
| Onboarding Initiation | 2676
| Onboarding Initiation request ( confidential hiring) | 1
| Poornata ID creation (Through External Hire) - Business | 5
| Position Creation/ Updation/ Deactivation | 1
| Process Queries | 9
| Request for Reports/Data (Other Modules) | 1
| Vendor Creation | 182
| Talent Staffing - Global | 3
| Blacklisting with Separation | 2
| Job Requisition Creation (Taleo updation and offer extension) | 14
TS Total |  | 20113
PMS | Approval of documents on system | 331
| Assign Goals to Employees | 12
| Business PMS Calendar Update | 34
| Cancellation of Probation Document | 56
| Cancelling of performance document | 1639
| Closure of performance document | 209
| Confirmation | 5
| Creation of performance document | 1993
| Creation of Probation Document | 6
| Data Change - Override Person Job Band | 1
| Data Change - Use Position Reports To | 4
| Goal library and sample goal updation | 0
| Job Data Update | 5
| null | 0
| PIP Document | 386
| Position Creation/ Updation/ Deactivation | 1
| Reopening of Manager Evaluation | 1473
| Reopening of Mid-year and Goal setting | 153
| Reopening of performance document | 128
| Reopening of Probation Document | 23
| Reopening of Self Evaluation | 210
| Report generation for talent discussions | 1
| Request for Reports/Data (PMS, Talent and Compensation) | 2
| Setup /Configuration Changes Required | 19
| Transfer of performance document | 3558
| Transfer of Probation Document | 20
| Transfer of Probation Documents | 20
| WFA Others | 1
| Create Venue | 1
PMS Total |  | 10291
JOB Arch | Data Change - Override Manager | 1
| null | 0
| Position creation/update | 8512
| Standard Job creation/update | 460
JOB Arch Total |  | 8973
LM | ABMCPL - 1st Day joining forms | 3
| Add new user-Bulk | 688
| Add Participants | 238
| Add Trainer | 10
| Adding/Deleting users in Channels/Groups | 16
| Admin Access Required | 623
| Attendance and Roster Updation | 337
| Compensation Update | 1
| Create evaluation form | 33
| Create Event(s) | 926
| Create Session(s) | 475
| Creating Online Courses | 1
| Creation and Assigning of Curriculum/ Deeplinks/ Online Courses/ Uploading Videos | 11
| Creation of Smartcards (Link/Video/Poll/Quiz/Text/SCORM/Live Event) | 4
| Custom report creation | 14
| Custom Reports | 40
| Data Change - Data Change | 0
| Domo Reports Access Request (GVC- Elearning) | 67
| Edit Event(s) | 8
| E-learning assignment | 137
| Exit_Approval reassignment for Clearance | 11
| Exit_Approval reassignment for Resignation | 3
| Exit_Resignation/Separation/ Termination | 10
| HR Process (Employee Self Services) / Education data | 10
| HR Process (Employee Self Services) / Marital Status | 2
| HR Process (Employee Self Services) / Name Change | 1
| Incident Class. / Admin / Tech Issues | 1
| Incident Class. / Errors / Bugs Identified | 18
| Incident Class. / Knowledge Query | 0
| Initiate Background Verification Check | 0
| Initiate EJF Verification Process | 5
| JD linkage | 16
| Job Data Update | 44
| Job Data Update (Resignation, Separation and Transfer) | 26
| Leave Balance upload | 8
| New/ Old Event | 2192
| New/ Old Session | 585
| null | 12
| Other Learning Activities | 742
| Personal Data Update | 58
| Poornata ID Creation (Add a Person) | 4
| Poornata ID creation (Through External Hire) - Business | 1
| Position Creation/ Updation/ Deactivation | 7
| Request for Reports/Data (Other Modules) | 192
| Setup /Configuration Changes Required | 187
| MDP bulk assignment | 525
| Learning Management | 0
| HR Process (Employee Self Services) / Address Change | 4
| Test related activities | 145
| Standard report generation | 2
| Create Venue | 3
| Add new user-Manual | 2
| Edit Session(s) | 0
| Add user to CSOD | 10
| (blank) | 7
LM Total |  | 8465
GVC | Add new user-Bulk | 542
| Adding/Deleting users in Channels/Groups | 30
| Admin Access Required | 12
| Creating Online Courses | 442
| Creation and Assigning of Curriculum/ Deeplinks/ Online Courses/ Uploading Videos | 2014
| Creation and editing of Channel/ Journeys/ Pathways/ Groups/ Smartcard | 549
| Creation of Smartcards (Link/Video/Poll/Quiz/Text/SCORM/Live Event) | 50
| Creation of Channels | 3
| Creation of Curriculum | 17
| Creation of Deeplinks | 360
| Custom report creation | 2
| Domo Reports Access Request (GVC- Elearning) | 142
| Domo Reports Request (Channel Consumption/ User Analytics/ Group Analytics) | 33
| E-learning assignment | 8
| GVC - elearning | 17
| HR Process (Employee Self Services) / Citizenship Details Passport | 1
| HR Process (Employee Self Services) / Education data | 2
| HR Process (Employee Self Services) / Marital Status | 2
| HR Process (Employee Self Services) / Name Change | 3
| Incident Class. / Access Issues | 38
| Incident Class. / Admin / Tech Issues | 15
| Incident Class. / Data / sync issue | 4
| Incident Class. / Errors / Bugs Identified | 43
| Incident Class. / Knowledge Query | 6
| null | 1
| Request for Reports/Data (Other Modules) | 4
| Setup /Configuration Changes Required | 110
| Training Course | 0
| Incident Class. / Portal Content Issues | 1
| Mapping certificate with course/curriculum/video | 2
| Uploading Videos | 38
| HR Process (Employee Self Services) / Address Change | 1
| Assigning Curriculum/ Courses/ Videos/ Materials | 1
| Access Required | 2
| Service Request Access Required | 0
| Data Request | 2
| Add new user-Manual | 2
| Assigning Content to users | 16
| Creation of Journeys/Pathways/Groups | 2
| (blank) | 4
GVC Total |  | 4521
ESS | Address Change | 9
| Education Data | 0
| Employee Self Service | 403
| HR Process (Employee Self Services) / Citizenship Details Passport | 49
| HR Process (Employee Self Services) / Education data | 190
| HR Process (Employee Self Services) / Marital Status | 43
| HR Process (Employee Self Services) / Name Change | 48
| Incident Class. / Bug due to data missing | 1
| Incident Class. / Data / sync issue | 1921
| Incident Class. / Errors / Bugs Identified | 1
| License and Certifications | 59
| Marital Status | 0
| Name Change | 23
| National id | 4
| Prior Work Experience | 2
| HR Process (Employee Self Services) / Address Change | 5
| HR Process (Employee Self Services) / License and Certifications | 48
| HR Process (Employee Self Services) / National ID | 2
| Education data | 283
| Marital Status | 36
| Citizenship Details Passport | 21
| Prior Work Experience | 17
| Incident Class. / Scheduled Activity / Process Failure | 0
| Incident Class. / System Downtime | 0
| (blank) | 350
ESS Total |  | 3515
LP | Job Requisition creation and On-boarding | 92
LP Total |  | 92
Rewards | AIP system setup - define/update plan goals and update business user access | 16
| APCR cycle first time administration | 6
Rewards Total |  | 22
Pratibha | Incident Class. / Data / sync issue | 1
| Incident Class. / Errors / Bugs Identified | 1
| Incident Class. / Knowledge Query | 5
Pratibha Total |  | 7
OE EE | Email response | 0
| (blank) | 1
OE EE Total |  | 1
Total |  | 320332

## Inventory (hidden)
Sr# | Transaction Name | Priority on Symphony (Filter Used) | Average Transactions (Annual) | Average Transactions (Monthly) | AHT Manual (In Min's) | Total AHT (HR) | Frequency | SLA | Response SLA Resolution SLA (Annual) | Processing Hours | Weekend BOT Run | Peak Period | RPA Priority | Applications Name | Tickets Containing OCR Documents (%) | OCR Required | Complexity | Impact | RPA AHT (Per Transaction) | Total Hrs (Daily) | Status
1 | Data Change – Override Manager | WFA_DTCHNG_OVRMGR-MEDIUM | 6089 | 507.4167 | 6 | 50.7417 | Daily | 24 Hrs | 98.81% 99.90% | Business Hours | Yes | March | 1 | Symphony, PeopleSoft Read from Excel | 30% | Non OCR | Medium | High |  |  | Deployed in Production
2 | Data Change – Use Position Reports To | WFA_DTCHNG_USEPOMGR_MEDIUM | 3933 | 327.75 | 5 | 27.3125 | Daily | 24 Hrs | 99.81% 99.90% | Business Hours | Yes | Jun-Aug | 2 | Symphony, PeopleSoft Read from Excel | 30% | Non OCR | Simple | High |  |  | Deployed in Production
3 | Job Architecture | Job Arch_Position_Creation/Updation_High (0-20) | 10692 | 891 | 5 | 74.25 | Daily | 12 Hrs | NA | Business Hours | Yes | Mar-Jun | 3 | Symphony, PeopleSoft Read from Excel | 0% | Non OCR | Medium | High |  |  | Deployed in Production
4 | Job Description Update | JAE and PM_JDLink_Low(1-330+) | 7168 | 597.3333 | 10 | 99.5556 | Daily | 12 Hrs | NA | Business Hours | Yes | May-Jul | 4 | Symphony, PeopleSoft Read from Excel | 0% | Non OCR | Complex | High |  |  | KT
5 | Data Change – Override Person Job Band | WFA_DTCHNG_OVRJB_MEDIUM | 4 | 0.33333 |  | 0 |  | 24 Hrs |  |  |  |  | 5 | Symphony, PeopleSoft Read from Excel | 0% | Non OCR
6 | Data Change – Use Position Job Band | WFA_DTCHNG_USPOJB_MEDIUM | 7 | 0.58333 |  | 0 |  | 24 Hrs |  |  |  |  | 6 | Symphony, PeopleSoft Read from Excel | 0% | Non OCR
7 | Data Change – Data Change | WFA_DTCHNG_DTCHNG_MEDIUM | 1372 | 114.3333 |  | 0 |  | 24 Hrs |  |  |  |  | 7 | Symphony, PeopleSoft Read from Excel | 0% | Non OCR
8 | External Hire Poornata ID creation | WFA_ExtHireB_High (80 or Less) | 5170 | 430.8333 |  | 0 | Daily | 12 Hrs |  |  |  |  | 8 | Symphony, PeopleSoft Read from Excel | 0% | Non OCR | Complex | High
| Poornata ID creation (Add a Person - Smart HR) | WFA_SmrtAddprsn_High | 1057 | 88.0833 | 5 | 7.35 | On Demand | 12 Hrs - If volume is less than 30 84 Hrs - if Volum is greater than 30 | [5 empty] | Symphony, PeopleSoft Read from Excel |  | Non OCR | Medium | Low
| Poornata ID Creation (Add a Person) - Excel Template | WFA_Addperson_High (85 or Less) | 5159 | 429.9167 | 20 | 143.31 | On Demand | 12 Hrs - If volume is less than 30 84 Hrs - if Volum is greater than 30 | [5 empty] | Symphony, PeopleSoft Read from Excel |  | Non OCR | Complex | High
| Poornata ID Creation (Add POI/CWR) | WFA_AddaPersnPOI/CWR_High (80 or Less) | 573 | 47.75 | 10 | 7.96 | On Demand | 12 Hrs - If volume is less than 30 84 Hrs - if Volum is greater than 30 | [5 empty] | Symphony, PeopleSoft Read from Excel |  | Non OCR | Complex | Low
9 | Job Data Update (Confirmation/Confirmation with pay rate change/Mobility) |  | 10119 | 843.25 | 5 | 70.28 | Daily | 12 Hrs |  | Business Hours |  |  |  | Symphony, PeopleSoft Read from Excel | 60% | OCR | Complex | High
10 | Personal Data Update (Excluding Bulk volume-43,274) | WFA_Prsnl_Low (1 to 240) | 14504 | 1208.6667 | 10 | 201.45 | Daily | 36 Hrs - If volume is less than 30 84 Hrs - if Volum is greater than 30 |  | Business Hours |  |  |  | Symphony, PeopleSoft Read from Excel | 20% | OCR | Complex | High
11 | Compensation Update (Excluding bulk volume-71,968) | WFA_JobUpd(Comp)_High ( 70 or Less) | 7232 | 602.6667 | 15 | 150.67 | Daily | 12 Hrs - If volume is less than 30 84 Hrs - if Volum is greater than 30 |  | Business Hours |  |  |  | Symphony, PeopleSoft Read from document/Excel | 20% | OCR | Complex | High
12 | Creation of Potential Assessment Document | TM_CrtPAD_High (1 to 30) | 5337 | 444.75 | 5 | 37.07 | Daily |  |  | Business Hours |  |  |  | Symphony, PeopleSoft Read from document/Excel | 0% | Non OCR | check with Anuja | High
13 | Poornata ID Creation (Add a Person) (Proposed Process Change) |  | 8925 | 743.75 | 25 | 309.9 |  | 12 Hrs | [5 empty] | Symphony, PeopleSoft Read from document/Excel | 90% | OCR | Complex
14 | Bank Data Update | WFA_BankDataUpdate_1-30_High | 3695 | 307.9167 | 8 | 41.06 | Weekly |  |  | Business Hours |  | Every Month 10th to 25th |  | Symphony, PeopleSoft Read from document/Excel | 90% | OCR | Medium | Medium
15 | Poornata ID creation (Through External Hire) – QC action and update if missing data-Proposed process change |  | 5854 | 487.8333 | 25 | 203.27 |  | 12 Hrs | [5 empty] | Onboarding tool, PeopleSoft Read from document/Excel | 90% | OCR
16 | Education Data | ESS_Edu_Low | 2981 | 248.4167 | 7 | 28.99 | Daily | 36 Hrs |  | Business Hours |  |  |  | Symphony, PeopleSoft Read from document/Excel | 90% | OCR | Complex | High
17 | National ID, PAN, Aadhar, Passport, Visa, Address | ESS_AddChg_Low ESS_Ppst_Low ESS_Visa_Low ESS_NationID_High | 495 | 41.25 | 10 | 6.88 | Weekly | 36 Hrs |  | Business Hours |  |  |  | Symphony, PeopleSoft Read from document/Excel | 90% | OCR | Medium | High
18 | Learning Session creation | LM_Crt_Sess_Medium (1 to 50) | 1277 | 106.4167 | 20 | 35.48 | Weekly | 24 Hrs |  | Business Hours |  |  |  | Symphony, CSOD Read from Excel | 0% | Non OCR |  | Medium
19 | Leave Balance upload | WFA_Leave Balance upload_Medium | 4243 | 353.5833 | 12 | 70.72 | Monthly | 24 Hrs |  | Business Hours |  | Every End Activity - Dec to Jan |  | Symphony, PeopleSoft Read from Excel | 0% | Non OCR | Complex | Medium
20 | BGV initiation and Report upload Initiate – 20 mins Report upload 10 mins | TS_BGV_Medium (1-30) | 5228 | 435.6667 | 30 | 217.84 | Daily | 24 Hrs |  | Business Hours |  |  |  | On boarding, One drive, Outlook and DMS | 0% | Non OCR | Complex | High
0
21 | FnF Settlement |  | 12829 | 1069.0833 |  | 0 | [7 empty] | Excel, Payroll system |  | non OCR | Complex | High
22 | Maker-Checker - ACR Letter |  |  |  |  | 0 | [7 empty] | People Soft, PDF, Excel |  | non OCR | Complex | High
23 | Ticket Creater |  | 48701 | 4058.4167 |  | 0 | Daily |  |  | Business Hours | Yes | year | 1 | Symphony, PeopleSoft Read from Excel |  | non OCR |  |  |  |  | Deployed in Production | 44643 | 4058.4545 | 48701.4545
24 | Talent Profile Creation BOT |  | 5310 | 442.5 |  | 0 | Based on requirement |  |  | Business Hours | Yes | year | 2 | PeopleSoft Read from Excel,PDF |  | non OCR |  |  |  |  | Deployed in Production
25 | Poornata Status update - SR Update in Transaction |  | 53182 | 4431.8333 |  | 0 | Daily |  |  | Business Hours | Yes | year | 1 | PeopleSoft Read from Excel |  | non OCR |  |  |  |  | Deployed in Production
26 | Audit Sampling |  |  |  |  | 0 | Based on requirement |  |  | Business Hours | Yes | year | 2 | Read from Excel |  | non OCR |  |  |  |  | Deployed in Production
27 | Create a Dashboard |  |  |  |  | 0 | Daily |  |  | Business Hours | Yes | year | 1 | Read from Excel,Outlook |  | non OCR
28 | Cement ticket creator |  |  |  |  | 0 | Daily |  |  | Business Hours | Yes | year | 1 | Symphony, PeopleSoft Read from Excel |  | non OCR
27 | Potential Assesment | Was built on Priority |  |  |  | 0 | Based on requirement |  |  | Business Hours | Yes | Oct-Dec | 1 | Symphony, PeopleSoft Read from Excel |  | non OCR |  |  |  |  | Deployed in Production
28 | PH Link Initiation (ABCAP) | TS_Onbrd_High | 6316 | 526.3333 | 10 |  | Daily | 12 Hrs |  | Business Hours | Yes | year |  | Symphony, ALT Recruit |  | OCR | Complex | High
| Total |  | 111114 |  | 233 | [13 empty] | 0 | 0

## Sheet1 (hidden)
Automation Required | Y
Count of UseCase Name | Column Labels
RPA UseCases | Complex | Medium | Simple | Grand Total
NON-OCR | 15 | 12 | 5 | 32
OCR | 8 | 1 |  | 9
Grand Total | 23 | 13 | 5 | 41

## Sheet2 (hidden)
Row Labels | Sum of Average Transactions (Annual)
NON-OCR | 284393
OCR | 174269
(blank)
Grand Total | 458662

## Complexity Guidelines
Parameter | Simple | Medium | Complex
Definitions | Tasks does not have any manual non digital inputs like | - Tasks have a maximum of simple binary decision-making steps like Yes/No etc. | - Tasks have handoffs between activities and the linkages have to be accurately managed.
| - Scanned images | - Data Transformation | - Nested Tasks / Activities
| - Unstructured data | - Application based Authentication Handing | - Multiple application interfaces
- Handwritten documents etc.
Number of applications used in the task? | 3 Max | 4 Max | 5 Max
(MS Excel, Outlook, SAP or a web browser, DB, Custom Application etc)
- In case of SAP / Web application, each tcode / screen or web page will be treated as a separate application
How many fields does the task have overall? (Sum the number of fields on all screens involved) | 01-35 | 35-75 | 75-125
What kind of decisions are taken to complete the task | The tasks is linear - there are no decisions to be taken | The tasks involves simple decisions (yes/no type) | The tasks involves complex & multiple decisions
Number of rules/conditions | 5 | 6 | 12
Multi Factor Authentication / Captcha / QR Code | No | Yes | Yes
Any task which cannot accomplish without Human supervision / checks (Example: Approvals, Digital Signature or any Complex decision) | No | No | Yes
Are any of the applications accessed via Citrix/VDI? | No | No | Yes
Is your input data only digital? | Yes | Yes | Yes
Input Channels Considered (Outlook, Files, ERP, Web downloads) | 2 | 4 | 6
Any task that require pattern recognition / Sentiment & Emotion Analysis (Example: Any decision making activity based on email received or any feedback survey) | No | No | Yes
Is your input data is structured/Unstructured? | Structured Excel, Word, Text Files | Form Based PDF, Fillable Word Forms | Unstructured Documents, Scanned Images, Handwritten Documents
Number of Files/file Types processed (Excel, Google Sheets, Word, .csv, .txt) | 3 | 5 | 7
Exception handling - Application and Logic | 6 Max | 10 Max | 15 Max

## ROI
Use Case Meta Data | [7 empty] | Existing Manual Daily Cost | [5 empty] | Savings |  | BOT Daily Cost | [8 empty] | ROI
#Priority | UseCase | Already in Production | AverageTransactions(Annual) | OCR/NON-OCR | Frequency | Complexity | Manual MHT / AHT in Min /Transaction | Manual FTE Required/Day | FTE Cost (Per Day) | Seat Cost (Per Day) | Employee Cost (Others - Paid by )* Per Day | Other OPEX Cost*Per Day | Total Cost (Per Day) | FTE Saved/Day | BOT MHT / AHT (Min) | BOT FTE Required / Day | FTE Cost After BOT Implementation(Per Day) | Infra Cost (Per Day) | License Cost (Per Day) |  |  | Development & Support |  | Total Cost (Excluding Development & Creater Cost) | ROI (Per Day) | ROI In Percent
[19 empty] | Runner | Creater | OCR | Development | Support
Overall Program ROI

## License
Total License |  |  | Bots Planned | Annual Transactions | Including 20% Buffer Transactions | Monthly Transactions | Daily Transactions | Daily Total time (Mins)
Runner License | 0 |  | 23 | 0 | 0 | 0 | 0 | #DIV/0!
Creator | 0 |  | Mins in 24 hours |  |  |  |  | 1440
|  |  | Runner Licenses |  |  |  |  | #DIV/0!
Allocated License |  |  | Evaluate every 3month based on Bots in production
Runner License | 0 | Existing Prod. Bots
Ticket Creation
Available |  |  | Bots Planned | Annual Transactions | Including 20% Buffer Transactions | Monthly Transactions | Daily Transactions | Daily Total time (Mins)
Runner License | 1 |  | 23 | 0 | 0 | 0 | 0 | #DIV/0!
| 1 |  | Mins in 12 hours |  |  |  |  | 720
Creator | 0 | Developer 1 | Runner Licenses |  |  |  |  | #DIV/0!
| 0 | Developer 2 | Evaluate every 3month based on Bots in production
| 0 | Developer 3
| 0 | Developer 4

## RPA RoadMap (hidden)
|  |  | 478662 |  |  |  | 54.6956 | 30.7327 | 28132600 | 18439644.6154 | 65.55% | >1500
| RPA Use Cases | [16 empty] | 2024 | [8 empty] | 2025 | [11 empty] | 2026
Sr# | UseCase Name |  | Average Transactions (Annual) | OCR / NON-OCR | Frequency | AHT (Manual) Mins | FTE Manual | FTE Saved | FTE Manual Cost (INR) | FTE Saved Cost (INR) | Already in production | Automation Required | RPA Complexity | Estimated Efforts(Weeks) | Developer | Timeline | Smonth | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
4 | Job Description Update |  | 7168 | NON-OCR | Daily | 10 | 0.91897 | 0.55138 | 551384.6154 | 330830.7692 | N | Y | Complex | 8.6 | Kishor | Mar-April | 202403 | 1
20 | National ID, PAN, Aadhar, Passport, Visa, Address |  | 9845 | OCR | Weekly | 10 | 1.2622 | 0.75731 | 757307.6923 | 454384.6154 | N | Y | Complex | 11.6 | Rutuja , RPADEV01 | April - May-June-July | 202404 | 1 | 1 | 1 | 1
17 | Bank Data Update |  | 3695 | OCR | Weekly | 8 | 0.37897 | 0.30318 | 227384.6154 | 181907.6923 | N | Y | Medium | 8.8 | Rutuja , RPADEV01 | April - May-June-July | 202404 | 1 | 1 | 1 | 1
19 | Education Data |  | 2981 | OCR | Daily | 7 | 0.26753 | 0.16052 | 160515.3846 | 96309.2308 | N | Y | Complex | 11.6 | Rutuja , RPADEV01 | April - May-June-July | 202404 | 1 | 1 | 1 | 1
24 | FnF Settlement |  | 12829 | NON-OCR | Monthly | 10 | 1.6447 | 0.98685 | 986846.1538 | 592107.6923 | N | Y | Complex | 8.6 | Ganesh / Tushar | April - May | 202404 | 1 | 1
38 | Holiday Schedule upload |  | 10287 | NON-OCR | Monthly | 10 | 1.3188 | 1.187 | 791307.6923 | 712176.9231 | N | Y | Simple | 4.8 | Kishor | May | 202405 |  | 1
41 | Job Data Update |  | 45835 | NON-OCR | Daily | 10 | 5.8763 | 4.701 | 3525769.2308 | 2820615.3846 | N | Y | Medium | 5.8 | Kishor | June- July | 202406 |  |  | 1 | 1
25 | Maker-Checker - ACR Letter |  | 5000 | NON-OCR | Annual | 10 | 0.64103 | 0.38462 | 384615.3846 | 230769.2308 | N | Y | Complex | 8.6 | Ganesh / Tushar | June- July -Aug | 202406 |  |  | 1 | 1 | 1
33 | PH Link Initiation (ABCAP) |  | 111114 | OCR | Daily | 10 | 14.2454 | 8.5472 | 8547230.7692 | 5128338.4615 | N | Y | Complex | 11.6 | Rutuja , RPADEV01 | Aug-Sep-Oct | 202408 |  |  |  |  | 1 | 1 | 1
16 | Poornata ID Creation (Add a Person) (Proposed Process Change) |  | 8925 | OCR | Daily | 25 | 2.8606 | 1.7163 | 1716346.1538 | 1029807.6923 | N | Y | Complex | 11.6 | Rutuja , RPADEV01 | Aug-Sep-Oct | 202408 |  |  |  |  | 1 | 1 | 1
18 | Poornata ID creation (Through External Hire) – QC action and update if missing data-Proposed process change |  | 5854 | OCR | Daily | 25 | 1.8763 | 1.1258 | 1125769.2308 | 675461.5385 | N | Y | Complex | 11.6 | Rutuja , RPADEV01 | Aug-Sep-Oct | 202408 |  |  |  |  | 1 | 1 | 1
46 | Position Creation/ Updation/ Deactivation and JD Linkage (Job Arch ???) |  | 9247 | NON-OCR | Daily | 10 | 1.1855 | 0.94841 | 711307.6923 | 569046.1538 | N | Y | Medium | 5.8 | Kishor | Aug-Sep | 202408 |  |  |  |  | 1 | 1
15 | Creation of Potential Assessment Document |  | 5337 | NON-OCR | Daily | 5 | 0.34212 | 0.20527 | 205269.2308 | 123161.5385 | N | Y | Complex | 8.6 | Kishor | Oct-Nov 2024 | 202410 | [6 empty] | 1 | 1
13 | Personal Data Update (Excluding Bulk volume-43,274) |  | 14504 | OCR | Daily | 10 | 1.8595 | 1.1157 | 1115692.3077 | 669415.3846 | N | Y | Complex | 11.6 | Rutuja , RPADEV01 | Nov-Dec-Jan-Feb | 202411 | [7 empty] | 1 | 1 | 1
12 | Job Data Update (Confirmation/Confirmation with pay rate change/Mobility) |  | 10119 | OCR | Daily | 5 | 0.64865 | 0.38919 | 389192.3077 | 233515.3846 | N | Y | Complex | 11.6 | Rutuja , RPADEV01 | Nov-Dec-Jan-Feb | 202411 | [7 empty] | 1 | 1 | 1
14 | Compensation Update (Excluding bulk volume-71,968) |  | 7232 | OCR | Daily | 15 | 1.3908 | 0.83446 | 834461.5385 | 500676.9231 | N | Y | Complex | 11.6 | Rutuja , RPADEV01 | Nov-Dec-Jan-Feb | 202411 | [7 empty] | 1 | 1 | 1
22 | Leave Balance upload |  | 4243 | NON-OCR | Monthly | 12 | 0.65277 | 0.39166 | 391661.5385 | 234996.9231 | N | Y | Complex | 8.6 | Kishor | Dec-Jan | 202412 | [8 empty] | 1 | 1
23 | BGV initiation and Report upload Initiate – 20 mins Report upload 10 mins |  | 5228 | NON-OCR | Daily | 30 | 2.0108 | 1.2065 | 1206461.5385 | 723876.9231 | N | Y | Complex | 8.6 | Rutuja | Feb-Mar 2025 | 202502 | [10 empty] | 1 | 1
34 | Cancelling of performance document |  | 1639 | NON-OCR | Annual | 10 | 0.21013 | 0.1681 | 126076.9231 | 100861.5385 | N | Y | Medium | 5.8 | Kishor | Feb-Mar 2025 | 202502 | [10 empty] | 1 | 1
35 | Creation and Assigning of Curriculum/ Deeplinks/ Online Courses/ Uploading Videos |  | 2025 | NON-OCR | Monthly | 10 | 0.25962 | 0.20769 | 155769.2308 | 124615.3846 | N | Y | Medium | 5.8 | Rutuja | Apr-May-25 | 202504 | [12 empty] | 1 | 1
36 | Creation of performance document |  | 2013 | NON-OCR | Annual | 10 | 0.25808 | 0.15485 | 154846.1538 | 92907.6923 | N | Y | Complex | 8.6 | Kishor | Apr-May-Jun-25 | 202504 | [12 empty] | 1 | 1 | 1
37 | Exit_Approval reassignment for Clearance |  | 1931 | NON-OCR | Monthly | 10 | 0.24756 | 0.14854 | 148538.4615 | 89123.0769 | N | Y | Complex | 8.6 | Rutuja | Jun-Jul-Aug-25 | 202506 | [14 empty] | 1 | 1 | 1
7 | Data Change – Data Change |  | 6804 | NON-OCR | Daily | 10 | 0.87231 | 0.69785 | 523384.6154 | 418707.6923 | N | Y | Medium | 5.8 | Kishor | 2025-07-01 | 202507 | [15 empty] | 1
40 | JD linkage |  | 4037 | NON-OCR | Daily | 10 | 0.51756 | 0.41405 | 310538.4615 | 248430.7692 | N | Y | Medium | 5.8 | Kishor | Aug-Sep-25 | 202508 | [16 empty] | 1 | 1
39 | Incident Class. / Data / sync issue |  | 1926 | NON-OCR | Daily | 10 | 0.24692 | 0.19754 | 148153.8462 | 118523.0769 | N | Y | Medium | 5.8 | Rutuja | Sep-Oct-25 | 202509 | [17 empty] | 1 | 1
42 | Job Data Update (Resignation, Separation and Transfer) |  | 4381 | NON-OCR | On Demand | 10 | 0.56167 | 0.44933 | 337000 | 269600 | N | Y | Medium | 5.8 | Kishor | Oct-Nov-25 | 202510 | [18 empty] | 1 | 1
43 | Mobility_HR Initiated Transfer |  | 7125 | NON-OCR | Monthly | 10 | 0.91346 | 0.73077 | 548076.9231 | 438461.5385 | N | Y | Medium | 5.8 | Rutuja | Jan-Feb-26 | 202511 | [19 empty] | 1 | 1
8 | External Hire Poornata ID creation |  | 5170 | NON-OCR | Daily | 10 | 0.66282 | 0.39769 | 397692.3077 | 238615.3846 | N | Y | Complex | 8.6 | Kishor | Nov-Dec-25 | 202512 | [20 empty] | 1 | 1
10 | Poornata ID Creation (Add a Person) - Excel Template |  | 5159 | NON-OCR | On Demand | 20 | 1.3228 | 0.79369 | 793692.3077 | 476215.3846 | N | Y | Complex | 8.6 | Kishor | Mar-Apr-26 | 202601 | [21 empty] | 1 | 1 | 1
44 | New/ Old Event |  | 2192 | NON-OCR | Daily | 10 | 0.28103 | 0.16862 | 168615.3846 | 101169.2308 | N | Y | Complex | 8.6 | Kishor | Dec-Jan-Feb-26 | 202602 | [22 empty] | 1 | 1
45 | Onboarding Initiation |  | 2676 | NON-OCR | Weekly | 10 | 0.34308 | 0.20585 | 205846.1538 | 123507.6923 | N | Y | Complex | 8.6 | Rutuja | Mar-Apr-May-26 | 202603 | [23 empty] | 1 | 1 | 1
1 | Data Change – Override Manager |  | 6089 | NON-OCR | Daily | 6 | 7.808 |  |  |  | Y | Y | Medium |  | Varun
2 | Data Change – Use Position Reports To |  | 3933 | NON-OCR | Daily | 5 |  |  |  |  | Y | Y | Simple |  | Varun
3 | Job Architecture |  | 10692 | NON-OCR | Daily | 5 |  |  |  |  | Y | Y | Medium |  | Varun
5 | Data Change – Override Person Job Band |  | 4 | NON-OCR |  | 0 | [5 empty] | N
6 | Data Change – Use Position Job Band |  | 7 | NON-OCR |  | 0 | [5 empty] | N
9 | Poornata ID creation (Add a Person - Smart HR) |  | 1057 | NON-OCR |  | 5 | [5 empty] | N
11 | Poornata ID Creation (Add POI/CWR) |  | 573 | NON-OCR |  | 10 | [5 empty] | N
21 | Learning Session creation |  | 1277 | NON-OCR |  | 20 | [5 empty] | N
26 | Ticket Creater |  | 48701 | NON-OCR | Daily | 10 |  |  |  |  | Y | Y | Complex |  | Varun
27 | Talent Profile Creation BOT | Peoplesoft feasiblity to download the selected profiles in bulk. Unattended BOT feasiblity | 5310 | NON-OCR | Based on requirement | 10 |  |  |  |  | Y | Y | Complex |  | Varun
28 | Poornata Status update - SR Update in Transaction | Child BOT of Ticket Creater | 53182 | NON-OCR | Daily | 10 |  |  |  |  | Y | Y | Simple |  | Viji
29 | Audit Sampling | Once in 15 days | 5000 | NON-OCR | Based on requirement | 10 |  |  |  |  | Y | Y | Simple |  | Viji
30 | Create a Dashboard | Centralized framework 1) Using powerapps,Onedrive 2) Bot Insights 3) using Oracle database & OCI Reports | 5000 | NON-OCR | Daily | 10 |  |  |  |  | Y | Y | Simple |  | Viji
31 | Cement ticket creator | Child BOT of Ticket Creater | 5000 | NON-OCR | Daily | 10 |  |  |  |  | Y | Y | Complex |  | Viji
32 | Potential Assesment | Peoplesoft feasiblity to check bulk creation. Unattended BOT feasiblity | 6316 | NON-OCR | Based on requirement | 10 | 0.80974 | 0.48585 | 485846.1538 | 291507.6923 | Y | Y | Medium |  | Viji
OBIEE Sync Failuer BOT

## RPA_SOP_Analysis_ABG Team SI-2 (hidden)
[9 empty] | 20% | 15% | 5% | 20% | 5% | 35% | 100%
UseCase Name | Comment | Priority | Average Transactions (Annual) | OCR / NON-OCR | Frequency | AHT (Manual) Mins | Document Referred | SOP Available | Manual Involvement | Complexity | Need Standardisation | Volume | Work with multiple data files | VOC | Scoring Index | Owner
National ID, PAN, Aadhar, Passport, Visa, Address |  | 6 | 9845 | OCR | Weekly | 10 | ESS SOP_National ID_SR to IM(2) | Y | 5 | 1 | 5 | 5 | 5 | 5 | 340 | Kunal
FnF Settlement |  | Parallel Execution | 12829 | NON-OCR | Monthly | 10 |  | N | 5 | 1 | 5 | 5 | 5 | 5 | 340 | Kunal
Initiate EJF Verification Process |  | 1 | 14999 | [5 empty] | 5 | 1 | 5 | 4 | 5 | 5 | 335
AWOO(A world of opprtunity) - OCR |  | 4 | 2700 | OCR | Yearly | 10 |  |  | 5 | 1 | 5 | 2 | 5 | 5 | 325 | Asawari
Education Data |  | 6 | 2981 | OCR | Daily | 7 | ESS SOP_Educational Data_SR to IM | Y | 5 | 1 | 5 | 2 | 5 | 5 | 325 | Kunal | SOP not shared but currently working on the project hence aware of the complexity. Sunil will share the SOP soon (as per Swara)
Pratibha - OCR |  | 3 | 540 | OCR | Yearly | 10 |  |  | 5 | 1 | 5 | 1 | 5 | 5 | 320
PH Link Initiation (ABCAP) | Not Required |  | 111114 | OCR | Daily | 10 | ABCAP SOP - Initiating Prospective Hire Link(2) | Y | 2 | 4 | 3 | 5 | 3 | 5 | 305
Exit_Approval reassignment for Clearance | Not Required |  | 1931 | NON-OCR | Monthly | 10 | Exit Module SOP_V.5 | Y | 3 | 5 | 1 | 2 | 1 | 4 | 282 | Kunal
Onboarding Initiation | Part of EJF | xxxx | 2676 | NON-OCR | Weekly | 10 | Alt Onboarding L5 V.2 | Y | 3 | 4 | 2 | 3 | 2 | 4 | 276 | Kunal
Poornata ID Creation (Add a Person) (Proposed Process Change) |  | 2 | 8925 | OCR | Daily | 25 |  | N | 2 | 4 | 5 | 4 | 1 | 4 | 265 | Kunal
Poornata ID creation (Through External Hire) – QC action and update if missing data-Proposed process change |  | 2 | 5854 | OCR | Daily | 25 |  | N | 2 | 4 | 5 | 3 | 1 | 4 | 260 | Asawari
Job Data Update (Excel Input / Bulk Data Update) |  | 9 | 45835 | NON-OCR | Daily | 10 |  | N | 4 | 1 | 5 | 5 | 1 | 3 | 230 | Abhishek
Data Change – Data Change | Need at later stage | xxxx | 6804 | NON-OCR | Daily | 10 |  | N | 3 | 3 | 5 | 3 | 1 | 3 | 230 | Abhishek
JD linkage | Not Required |  | 4037 | NON-OCR | Daily | 10 | JD Update SOP | Y | 1 | 3 | 5 | 3 | 1 | 4 | 225
Job Data Update (Resignation, Separation and Transfer) | Duplicate |  | 4381 | NON-OCR | On Demand | 10 | JD Update SOP | Y | 1 | 3 | 5 | 3 | 1 | 4 | 225 | Poonam
Mobility_HR Initiated Transfer | Duplicate |  | 7125 | OCR | Monthly | 10 | Mobility SOP | Y | 1 | 5 | 1 | 4 | 3 | 3 | 219 | Kunal
Transfer of performance document | Check script option | 8 | 3558 | [5 empty] | 2 | 5 | 5 | 3 | 1 | 2 | 205 | Asawari
Creation of performance document | Exception Management |  | 2013 | NON-OCR | Annual | 10 | SOP_Creation of Performance Document | Y | 4 | 5 | 5 | 2 | 5 |  | 190 | Asawari
Job Description Update |  | 0 | 7168 | NON-OCR | Daily | 10 | JD Update SOP | Y | 2 | 4 | 4 | 3 | 1 | 1 | 152 | Asawari
Holiday Schedule upload |  | 7 | 10287 | NON-OCR | Monthly | 10 | Holiday Calender Upload SOP | Y | 1 | 5 | 5 | 1 | 1 | 1 | 140 | Kunal
Cancelling of performance document | Already backend script available |  | 1639 | NON-OCR | Annual | 10 | SOP_Cancellation of Performance Document | Y | 3 | 3 | 5 | 2 | 5 |  | 140 | Kunal
Leave Balance upload | Not Required |  | 4243 | NON-OCR | Monthly | 12 | Leave Balance Upload SOP_V3 | Y | 1 | 5 | 5 | 4 | 5 |  | 140 | Kunal
Bank Data Update |  | 5 | 3695 | OCR | Weekly | 8 | WFA Global SOP | Y | 1 | 4 | 5 | 2 | 1 | 1 | 130 | Abhishek
Creation and Assigning of Curriculum/ Deeplinks/ Online Courses/ Uploading Videos | Learning | TBD | 2025 | NON-OCR | Monthly | 10 | SOP_CSOD_Creation & Assign Curriculum SOP_CSOD_Upload and Assign Online course_V1 SOP_CSOD_Upload and Assign Video_V1 | Y | 1 | 5 | 5 | 2 | 5 |  | 130 | Abhishek
New/ Old Event | Learning | TBD | 2192 | NON-OCR | Daily | 10 | Creating Event, Session & Adding Trainer - Group Creation SOP | Y | 2 | 3 | 1 | 2 | 1 | 1 | 127 | Abhishek
Creation of Potential Assessment Document | Already there - Not required |  | 5337 | NON-OCR | Daily | 5 | SOP_Potential Management_Creation of Potential Assessment Document | Y | 2 | 2 | 1 | 1 | 1 | 1 | 111 | Abhishek
Position Creation/ Updation/ Deactivation and JD Linkage (Job Arch) | Already in Production | 0 | 9247 | NON-OCR | Daily | 10 |  | N | [6 empty] | 0 | Poonam
Incident Class. / Data / sync issue | Learning | TBD | 1926 | NON-OCR | Daily | 10 |  | N | [6 empty] | 0 | Poonam
Maker-Checker - ACR Letter | To be confirmed |  | 5000 | NON-OCR | Annual | 10 |  | N | [6 empty] | 0 | Poonam
Personal Data Update (Excluding Bulk volume-43,274) | Assess Selenium Current build |  | 14504 | NON-OCR | Daily | 10 |  | N | [6 empty] | 0 | Poonam
Job Data Update (Confirmation/Confirmation with pay rate change/Mobility) | TBD- Peoplesoft Letter generation Built |  | 10119 | OCR | Daily | 5 |  | N | [6 empty] | 0 | Poonam
Compensation Update (Excluding bulk volume-71,968) | Not Required |  | 7232 | OCR | Daily | 15 |  | N |  |  |  | 5 |  |  | 0 | Poonam
BGV initiation and Report upload Initiate – 20 mins Report upload 10 mins | Not Required |  | 5228 | NON-OCR | Daily | 30 |  | N |  |  |  | 5 |  |  | 0 | Poonam
External Hire Poornata ID creation | Duplicate |  | 5170 | NON-OCR | Daily | 10 |  | N | [6 empty] | 0 | Poonam
Poornata ID Creation (Add a Person) - Excel Template | Duplicate |  | 5159 | NON-OCR | On Demand | 20 |  | N | [6 empty] | 0 | Asawari
Report generation for talent discussions | Already BOT present |  | 6131
Position creation/update | Duplicate |  | 8512
Note on G6: Average Document Verification Time
Note on G8: Average Document Verification Time

## RPA_SOP_Analysis_ABG Team (hidden)
[9 empty] | 20% | 15% | 5% | 20% | 5% | 35% | 100%
UseCase Name | Comment | Priority | Average Transactions (Annual) | OCR / NON-OCR | Frequency | AHT (Manual) Mins | Document Referred | SOP Available | Manual Involvement | Complexity | Need Standardisation | Volume | Work with multiple data files | VOC | Scoring Index | Owner
Job Description Update |  | 0 | 7168 | NON-OCR | Daily | 10 | JD Update SOP | Y | 2 | 2 | 2 | 3 | 1 | 1 | 116 | Kunal
Position Creation/ Updation/ Deactivation and JD Linkage (Job Arch) | Already in Production | 0 | 9247 | NON-OCR | Daily | 10 |  | N | [6 empty] | 0 | Kunal
Initiate EJF Verification Process |  | 1 | 12516 | [5 empty] | 5 | 5 | 1 | 4 | 5 | 5 | 379
Poornata ID Creation (Add a Person) (Proposed Process Change) |  | 2 | 8925 | OCR | Daily | 25 |  | N | 2 | 2 | 1 | 4 | 1 | 4 | 219 | Asawari
Poornata ID creation (Through External Hire) – QC action and update if missing data-Proposed process change |  | 2 | 5854 | OCR | Daily | 25 |  | N | 2 | 2 | 1 | 3 | 1 | 4 | 218 | Kunal | SOP not shared but currently working on the project hence aware of the complexity. Sunil will share the SOP soon (as per Swara)
Pratibha |  | 3 | 540 | OCR | Yearly | 10 |  |  | 5 | 5 | 1 | 1 | 5 | 5 | 376
AWOO(A world of opprtunity) |  | 4 | 2700 | OCR | Yearly | 10 |  |  | 5 | 5 | 1 | 2 | 5 | 5 | 377
Bank Data Update |  | 5 | 3695 | OCR | Weekly | 8 | WFA Global SOP | Y | 1 | 2 | 1 | 2 | 1 | 1 | 92 | Kunal
National ID, PAN, Aadhar, Passport, Visa, Address |  | 6 | 9845 | OCR | Weekly | 10 | ESS SOP_National ID_SR to IM(2) | Y | 5 | 5 | 1 | 5 | 5 | 5 | 380 | Kunal
Education Data |  | 6 | 2981 | OCR | Daily | 7 | ESS SOP_Educational Data_SR to IM | Y | 5 | 5 | 1 | 2 | 5 | 5 | 377 | Kunal
Holiday Schedule upload |  | 7 | 10287 | NON-OCR | Monthly | 10 | Holiday Calender Upload SOP | Y | 1 | 1 | 1 | 1 | 1 | 1 | 76 | Asawari
Creation of performance document | Exception Management |  | 2013 | NON-OCR | Annual | 10 | SOP_Creation of Performance Document | Y | 4 | 5 | 5 | 2 | 5 |  | 190 | Abhishek
Cancelling of performance document | Already backend script available |  | 1639 | NON-OCR | Annual | 10 | SOP_Cancellation of Performance Document | Y | 3 | 3 | 5 | 2 | 5 |  | 140 | Abhishek
Transfer of performance document | Check script option | 8 | 3558 | [5 empty] | 2 | 1 | 1 | 3 | 1 | 2 | 133
Data Change – Data Change | Need at later stage | xxxx | 6804 | NON-OCR | Daily | 10 |  | N | 3 | 3 | 1 | 3 | 1 | 3 | 218 | Poonam
FnF Settlement |  | Parallel Execution | 12829 | NON-OCR | Monthly | 10 |  | N | 5 | 5 | 1 | 5 | 5 | 5 | 380 | Kunal
Job Data Update (Excel Input / Bulk Data Update) |  | 9 | 45835 | NON-OCR | Daily | 10 |  | N | 4 | 5 | 1 | 5 | 1 | 3 | 270 | Asawari
Maker-Checker - ACR Letter | To be confirmed |  | 5000 | NON-OCR | Annual | 10 |  | N | [6 empty] | 0 | Asawari
PH Link Initiation (ABCAP) | Not Required |  | 111114 | OCR | Daily | 10 | ABCAP SOP - Initiating Prospective Hire Link(2) | Y | 2 | 4 | 3 | 5 | 3 | 5 | 305 | Asawari
Creation of Potential Assessment Document | Already there - Not required |  | 5337 | NON-OCR | Daily | 5 | SOP_Potential Management_Creation of Potential Assessment Document | Y | 2 | 2 | 1 | 1 | 1 | 1 | 111 | Kunal
Personal Data Update (Excluding Bulk volume-43,274) | Assess Selenium Current build |  | 14504 | NON-OCR | Daily | 10 |  | N | [6 empty] | 0 | Kunal
Job Data Update (Confirmation/Confirmation with pay rate change/Mobility) | TBD- Peoplesoft Letter generation Built |  | 10119 | OCR | Daily | 5 |  | N | [6 empty] | 0 | Kunal
Compensation Update (Excluding bulk volume-71,968) | Not Required |  | 7232 | OCR | Daily | 15 |  | N |  |  |  | 5 |  |  | 0 | Abhishek
Leave Balance upload | Not Required |  | 4243 | NON-OCR | Monthly | 12 | Leave Balance Upload SOP_V3 | Y | 1 | 5 | 5 | 4 | 5 |  | 140 | Abhishek
BGV initiation and Report upload Initiate – 20 mins Report upload 10 mins | Not Required |  | 5228 | NON-OCR | Daily | 30 |  | N |  |  |  | 5 |  |  | 0 | Abhishek
Creation and Assigning of Curriculum/ Deeplinks/ Online Courses/ Uploading Videos | Learning | TBD | 2025 | NON-OCR | Monthly | 10 | SOP_CSOD_Creation & Assign Curriculum SOP_CSOD_Upload and Assign Online course_V1 SOP_CSOD_Upload and Assign Video_V1 | Y | 1 | 5 | 5 | 2 | 5 |  | 130 | Abhishek
Exit_Approval reassignment for Clearance | Not Required |  | 1931 | NON-OCR | Monthly | 10 | Exit Module SOP_V.5 | Y | 3 | 5 | 1 | 2 | 1 | 4 | 282 | Poonam
JD linkage | Not Required |  | 4037 | NON-OCR | Daily | 10 | JD Update SOP | Y | 1 | 3 | 5 | 3 | 1 | 4 | 225 | Poonam
Incident Class. / Data / sync issue | Learning | TBD | 1926 | NON-OCR | Daily | 10 |  | N | [6 empty] | 0 | Poonam
Job Data Update (Resignation, Separation and Transfer) | Duplicate |  | 4381 | NON-OCR | On Demand | 10 | JD Update SOP | Y | 1 | 3 | 5 | 3 | 1 | 4 | 225 | Poonam
Mobility_HR Initiated Transfer | Duplicate |  | 7125 | OCR | Monthly | 10 | Mobility SOP | Y | 1 | 5 | 1 | 4 | 3 | 3 | 219 | Poonam
External Hire Poornata ID creation | Duplicate |  | 5170 | NON-OCR | Daily | 10 |  | N | [6 empty] | 0 | Poonam
Poornata ID Creation (Add a Person) - Excel Template | Duplicate |  | 5159 | NON-OCR | On Demand | 20 |  | N | [6 empty] | 0 | Poonam
New/ Old Event | Learning | TBD | 2192 | NON-OCR | Daily | 10 | Creating Event, Session & Adding Trainer - Group Creation SOP | Y | 2 | 3 | 1 | 2 | 1 | 1 | 127 | Poonam
Onboarding Initiation | Part of EJF | xxxx | 2676 | NON-OCR | Weekly | 10 | Alt Onboarding L5 V.2 | Y | 3 | 4 | 2 | 3 | 2 | 4 | 276 | Asawari
Report generation for talent discussions | Already BOT present |  | 6131
Position creation/update | Duplicate |  | 8512
Note on G8: Average Document Verification Time
Note on G9: Average Document Verification Time

## RPA_SOP_Analysis_ABG Team SI (hidden)
[9 empty] | 20% | 15% | 5% | 20% | 5% | 35% | 100%
UseCase Name | Comment | Priority | Average Transactions (Annual) | OCR / NON-OCR | Frequency | AHT (Manual) Mins | Document Referred | SOP Available | Manual Involvement | Complexity | Need Standardisation | Volume | Work with multiple data files | VOC | Scoring Index | Owner
National ID, PAN, Aadhar, Passport, Visa, Address |  | 6 | 9845 | OCR | Weekly | 10 | ESS SOP_National ID_SR to IM(2) | Y | 5 | 1 | 5 | 5 | 5 | 5 | 340 | Kunal
FnF Settlement |  | Parallel Execution | 12829 | NON-OCR | Monthly | 10 |  | N | 5 | 1 | 5 | 5 | 5 | 5 | 340 | Kunal
Initiate EJF Verification Process |  | 1 | 14999 | [5 empty] | 5 | 1 | 5 | 4 | 5 | 5 | 335
AWOO(A world of opprtunity) |  | 4 | 2700 | OCR | Yearly | 10 |  |  | 5 | 1 | 5 | 2 | 5 | 5 | 325 | Asawari
Education Data |  | 6 | 2981 | OCR | Daily | 7 | ESS SOP_Educational Data_SR to IM | Y | 5 | 1 | 5 | 2 | 5 | 5 | 325 | Kunal | SOP not shared but currently working on the project hence aware of the complexity. Sunil will share the SOP soon (as per Swara)
Pratibha |  | 3 | 540 | OCR | Yearly | 10 |  |  | 5 | 1 | 5 | 1 | 5 | 5 | 320
PH Link Initiation (ABCAP) | Not Required |  | 111114 | OCR | Daily | 10 | ABCAP SOP - Initiating Prospective Hire Link(2) | Y | 2 | 4 | 3 | 5 | 3 | 5 | 305
Exit_Approval reassignment for Clearance | Not Required |  | 1931 | NON-OCR | Monthly | 10 | Exit Module SOP_V.5 | Y | 3 | 5 | 1 | 2 | 1 | 4 | 282 | Kunal
Onboarding Initiation | Part of EJF | xxxx | 2676 | NON-OCR | Weekly | 10 | Alt Onboarding L5 V.2 | Y | 3 | 4 | 2 | 3 | 2 | 4 | 276 | Kunal
Poornata ID Creation (Add a Person) (Proposed Process Change) |  | 2 | 8925 | OCR | Daily | 25 |  | N | 2 | 4 | 5 | 4 | 1 | 4 | 265 | Kunal
Poornata ID creation (Through External Hire) – QC action and update if missing data-Proposed process change |  | 2 | 5854 | OCR | Daily | 25 |  | N | 2 | 4 | 5 | 3 | 1 | 4 | 260 | Asawari
Job Data Update (Excel Input / Bulk Data Update) |  | 9 | 45835 | NON-OCR | Daily | 10 |  | N | 4 | 1 | 5 | 5 | 1 | 3 | 230 | Abhishek
Data Change – Data Change | Need at later stage | xxxx | 6804 | NON-OCR | Daily | 10 |  | N | 3 | 3 | 5 | 3 | 1 | 3 | 230 | Abhishek
JD linkage | Not Required |  | 4037 | NON-OCR | Daily | 10 | JD Update SOP | Y | 1 | 3 | 5 | 3 | 1 | 4 | 225
Job Data Update (Resignation, Separation and Transfer) | Duplicate |  | 4381 | NON-OCR | On Demand | 10 | JD Update SOP | Y | 1 | 3 | 5 | 3 | 1 | 4 | 225 | Poonam
Mobility_HR Initiated Transfer | Duplicate |  | 7125 | OCR | Monthly | 10 | Mobility SOP | Y | 1 | 5 | 1 | 4 | 3 | 3 | 219 | Kunal
Transfer of performance document | Check script option | 8 | 3558 | [5 empty] | 2 | 5 | 5 | 3 | 1 | 2 | 205 | Asawari
Creation of performance document | Exception Management |  | 2013 | NON-OCR | Annual | 10 | SOP_Creation of Performance Document | Y | 4 | 5 | 5 | 2 | 5 |  | 190 | Asawari
Job Description Update |  | 0 | 7168 | NON-OCR | Daily | 10 | JD Update SOP | Y | 2 | 4 | 4 | 3 | 1 | 1 | 152 | Asawari
Holiday Schedule upload |  | 7 | 10287 | NON-OCR | Monthly | 10 | Holiday Calender Upload SOP | Y | 1 | 5 | 5 | 1 | 1 | 1 | 140 | Kunal
Cancelling of performance document | Already backend script available |  | 1639 | NON-OCR | Annual | 10 | SOP_Cancellation of Performance Document | Y | 3 | 3 | 5 | 2 | 5 |  | 140 | Kunal
Leave Balance upload | Not Required |  | 4243 | NON-OCR | Monthly | 12 | Leave Balance Upload SOP_V3 | Y | 1 | 5 | 5 | 4 | 5 |  | 140 | Kunal
Bank Data Update |  | 5 | 3695 | OCR | Weekly | 8 | WFA Global SOP | Y | 1 | 4 | 5 | 2 | 1 | 1 | 130 | Abhishek
Creation and Assigning of Curriculum/ Deeplinks/ Online Courses/ Uploading Videos | Learning | TBD | 2025 | NON-OCR | Monthly | 10 | SOP_CSOD_Creation & Assign Curriculum SOP_CSOD_Upload and Assign Online course_V1 SOP_CSOD_Upload and Assign Video_V1 | Y | 1 | 5 | 5 | 2 | 5 |  | 130 | Abhishek
New/ Old Event | Learning | TBD | 2192 | NON-OCR | Daily | 10 | Creating Event, Session & Adding Trainer - Group Creation SOP | Y | 2 | 3 | 1 | 2 | 1 | 1 | 127 | Abhishek
Creation of Potential Assessment Document | Already there - Not required |  | 5337 | NON-OCR | Daily | 5 | SOP_Potential Management_Creation of Potential Assessment Document | Y | 2 | 2 | 1 | 1 | 1 | 1 | 111 | Abhishek
Position Creation/ Updation/ Deactivation and JD Linkage (Job Arch) | Already in Production | 0 | 9247 | NON-OCR | Daily | 10 |  | N | [6 empty] | 0 | Poonam
Incident Class. / Data / sync issue | Learning | TBD | 1926 | NON-OCR | Daily | 10 |  | N | [6 empty] | 0 | Poonam
Maker-Checker - ACR Letter | To be confirmed |  | 5000 | NON-OCR | Annual | 10 |  | N | [6 empty] | 0 | Poonam
Personal Data Update (Excluding Bulk volume-43,274) | Assess Selenium Current build |  | 14504 | NON-OCR | Daily | 10 |  | N | [6 empty] | 0 | Poonam
Job Data Update (Confirmation/Confirmation with pay rate change/Mobility) | TBD- Peoplesoft Letter generation Built |  | 10119 | OCR | Daily | 5 |  | N | [6 empty] | 0 | Poonam
Compensation Update (Excluding bulk volume-71,968) | Not Required |  | 7232 | OCR | Daily | 15 |  | N |  |  |  | 5 |  |  | 0 | Poonam
BGV initiation and Report upload Initiate – 20 mins Report upload 10 mins | Not Required |  | 5228 | NON-OCR | Daily | 30 |  | N |  |  |  | 5 |  |  | 0 | Poonam
External Hire Poornata ID creation | Duplicate |  | 5170 | NON-OCR | Daily | 10 |  | N | [6 empty] | 0 | Poonam
Poornata ID Creation (Add a Person) - Excel Template | Duplicate |  | 5159 | NON-OCR | On Demand | 20 |  | N | [6 empty] | 0 | Asawari
Report generation for talent discussions | Already BOT present |  | 6131
Position creation/update | Duplicate |  | 8512
Note on G6: Average Document Verification Time
Note on G8: Average Document Verification Time

## RPA_SOP_Analysis (hidden)
[7 empty] | 20% | 15% | 5% | 20% | 5% | 30% | 5% | 100%
UseCase Name | Average Transactions (Annual) | OCR / NON-OCR | Frequency | AHT (Manual) Mins | Document Referred | SOP Available | Manual Involvement | Complexity | Need Standardisation | Volume | Work with multiple data files | VOC | Service Quality | Scoring Index | Owner
Job Description Update | 7168 | NON-OCR | Daily | 10 | JD Update SOP | Y | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 92 | Kunal
National ID, PAN, Aadhar, Passport, Visa, Address | 9845 | OCR | Weekly | 10 | ESS SOP_National ID_SR to IM(2) | Y | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 116 | Kunal
Bank Data Update | 3695 | OCR | Weekly | 8 | WFA Global SOP | Y | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 96 | Kunal
Education Data | 2981 | OCR | Daily | 7 | ESS SOP_Educational Data_SR to IM | Y | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 116 | Kunal
FnF Settlement | 12829 | NON-OCR | Monthly | 10 |  | N | 2 | 3 | 1 | 2 | 3 | 2 | 1 | 167 | Kunal | SOP not shared but currently working on the project hence aware of the complexity. Sunil will share the SOP soon (as per Swara)
Holiday Schedule upload | 10287 | NON-OCR | Monthly | 10 | Holiday Calender Upload SOP | Y | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 76 | Asawari
Job Data Update | 45835 | NON-OCR | Daily | 10 |  | N | [7 empty] | 0 | Asawari
Maker-Checker - ACR Letter | 5000 | NON-OCR | Annual | 10 |  | N | [7 empty] | 0 | Asawari
PH Link Initiation (ABCAP) | 111114 | OCR | Daily | 10 | ABCAP SOP - Initiating Prospective Hire Link(2) | Y | 2 | 4 | 3 | 5 | 3 | 5 | 4 | 300 | Asawari
Poornata ID Creation (Add a Person) (Proposed Process Change) | 8925 | OCR | Daily | 25 |  | N | [7 empty] | 0 | Asawari
Poornata ID creation (Through External Hire) – QC action and update if missing data-Proposed process change | 5854 | OCR | Daily | 25 |  | N | [7 empty] | 0 | Kunal
Position Creation/ Updation/ Deactivation and JD Linkage (Job Arch ???) | 9247 | NON-OCR | Daily | 10 |  | N | [7 empty] | 0 | Kunal
Creation of Potential Assessment Document | 5337 | NON-OCR | Daily | 5 | SOP_Potential Management_Creation of Potential Assessment Document | Y | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 111 | Kunal
Personal Data Update (Excluding Bulk volume-43,274) | 14504 | OCR | Daily | 10 |  | N | [7 empty] | 0 | Kunal
Job Data Update (Confirmation/Confirmation with pay rate change/Mobility) | 10119 | OCR | Daily | 5 |  | N | [7 empty] | 0 | Kunal
Compensation Update (Excluding bulk volume-71,968) | 7232 | OCR | Daily | 15 |  | N |  |  |  | 5 |  |  |  | 0 | Abhishek
Leave Balance upload | 4243 | NON-OCR | Monthly | 12 | Leave Balance Upload SOP_V3 | Y | 1 | 5 | 5 | 4 | 5 |  |  | 140 | Abhishek
BGV initiation and Report upload Initiate – 20 mins Report upload 10 mins | 5228 | NON-OCR | Daily | 30 |  | N |  |  |  | 5 |  |  |  | 0 | Abhishek
Cancelling of performance document | 1639 | NON-OCR | Annual | 10 | SOP_Cancellation of Performance Document | Y | 3 | 3 | 5 | 2 | 5 |  |  | 140 | Abhishek
Creation and Assigning of Curriculum/ Deeplinks/ Online Courses/ Uploading Videos | 2025 | NON-OCR | Monthly | 10 | SOP_CSOD_Creation & Assign Curriculum SOP_CSOD_Upload and Assign Online course_V1 SOP_CSOD_Upload and Assign Video_V1 | Y | 1 | 5 | 5 | 2 | 5 |  |  | 130 | Abhishek
Creation of performance document | 2013 | NON-OCR | Annual | 10 | SOP_Creation of Performance Document | Y | 4 | 5 | 5 | 2 | 5 |  |  | 190 | Abhishek
Exit_Approval reassignment for Clearance | 1931 | NON-OCR | Monthly | 10 | Exit Module SOP_V.5 | Y | 3 | 5 | 1 | 2 | 1 | 4 | 5 | 287 | Poonam
Data Change – Data Change | 6804 | NON-OCR | Daily | 10 |  | N | [7 empty] | 0 | Poonam
JD linkage | 4037 | NON-OCR | Daily | 10 | JD Update SOP | Y | 1 | 3 | 5 | 3 | 1 | 4 | 3 | 220 | Poonam
Incident Class. / Data / sync issue | 1926 | NON-OCR | Daily | 10 |  | N | [7 empty] | 0 | Poonam
Job Data Update (Resignation, Separation and Transfer) | 4381 | NON-OCR | On Demand | 10 | JD Update SOP | Y | 1 | 3 | 5 | 3 | 1 | 4 | 3 | 220 | Poonam
Mobility_HR Initiated Transfer | 7125 | OCR | Monthly | 10 | Mobility SOP | Y | 1 | 5 | 1 | 4 | 3 | 3 | 5 | 229 | Poonam
External Hire Poornata ID creation | 5170 | NON-OCR | Daily | 10 |  | N | [7 empty] | 0 | Poonam
Poornata ID Creation (Add a Person) - Excel Template | 5159 | NON-OCR | On Demand | 20 |  | N | [7 empty] | 0 | Poonam
New/ Old Event | 2192 | NON-OCR | Daily | 10 | Creating Event, Session & Adding Trainer - Group Creation SOP | Y | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 127 | Poonam
Onboarding Initiation | 2676 | NON-OCR | Weekly | 10 | Alt Onboarding L5 V.2 | Y | 3 | 4 | 2 | 3 | 2 | 4 | 4 | 276 | Asawari

## Gantt (hidden)
RPA Use Cases |  |  | 2024 | [8 empty] | 2025 | [11 empty] | 2026
Use Case Name | Average Transactions (Annual) | OCR / NON-OCR | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Job Description Update | 7168 | NON-OCR | bar: 2024 Apr
National ID, PAN, Aadhar, Passport, Visa, Address | 9845 | OCR | bar: 2024 Apr to 2024 Jul
Bank Data Update | 3695 | OCR | bar: 2024 Apr to 2024 Jul
Education Data | 2981 | OCR | bar: 2024 Apr to 2024 Jul
FnF Settlement | 12829 | NON-OCR | bar: 2024 Apr to 2024 May
Holiday Schedule upload | 10287 | NON-OCR | bar: 2024 May
Job Data Update | 45835 | NON-OCR | bar: 2024 Jun to 2024 Jul
Maker-Checker - ACR Letter |  | NON-OCR | bar: 2024 Jun to 2024 Aug
PH Link Initiation (ABCAP) | 111114 | OCR | bar: 2024 Aug to 2024 Oct
Poornata ID Creation (Add a Person) (Proposed Process Change) | 8925 | OCR | bar: 2024 Aug to 2024 Oct
Poornata ID creation (Through External Hire) | 5854 | OCR | bar: 2024 Aug to 2024 Oct
Position Creation/ Updation/ Deactivation and JD Linkage (Job Arch ???) | 9247 | NON-OCR | bar: 2024 Aug to 2024 Sep
Creation of Potential Assessment Document | 5337 | NON-OCR | bar: 2024 Oct to 2024 Nov
Personal Data Update (Excluding Bulk volume-43,274) | 14504 | OCR | bar: 2024 Nov to 2025 Jan
Job Data Update (Confirmation/Confirmation with pay rate change/Mobility) | 10119 | OCR | bar: 2024 Nov to 2025 Jan
Compensation Update (Excluding bulk volume-71,968) | 7232 | OCR | bar: 2024 Nov to 2025 Jan
Leave Balance upload | 4243 | NON-OCR | bar: 2024 Dec to 2025 Jan
BGV initiation and Report upload Initiate – 20 mins Report upload 10 mins | 5228 | NON-OCR | bar: 2025 Feb to 2025 Mar
Cancelling of performance document | 1639 | NON-OCR | bar: 2025 Feb to 2025 Mar
Creation and Assigning of Curriculum/ Deeplinks/ Online Courses/ Uploading Videos | 2025 | NON-OCR | bar: 2025 Apr to 2025 May
Creation of performance document | 2013 | NON-OCR | bar: 2025 Apr to 2025 Jun
Exit_Approval reassignment for Clearance | 1931 | NON-OCR | bar: 2025 Jun to 2025 Aug
Data Change – Data Change | 6804 | NON-OCR | bar: 2025 Jul
JD linkage | 4037 | NON-OCR | bar: 2025 Aug to 2025 Sep
Incident Class. / Data / sync issue | 1926 | NON-OCR | bar: 2025 Sep to 2025 Oct
Job Data Update (Resignation, Separation and Transfer) | 4381 | NON-OCR | bar: 2025 Oct to 2025 Nov
Mobility_HR Initiated Transfer | 7125 | NON-OCR | bar: 2025 Nov to 2025 Dec
External Hire Poornata ID creation | 5170 | NON-OCR | bar: 2025 Dec to 2026 Jan
Poornata ID Creation (Add a Person) - Excel Template | 5159 | NON-OCR | bar: 2026 Jan to 2026 Mar
New/ Old Event | 2192 | NON-OCR | bar: 2026 Feb to 2026 Mar
Onboarding Initiation | 2676 | NON-OCR | bar: 2026 Mar to 2026 May

## RPA ProcessCount_Frequency (hidden)
Count of UseCase Name | Column Labels
Row Labels | Annual | Based on requirement | Daily | Monthly | On Demand | Weekly | Grand Total
NON-OCR | 3 | 3 | 17 | 6 | 2 | 1 | 32
OCR |  |  | 7 |  |  | 2 | 9
Grand Total | 3 | 3 | 24 | 6 | 2 | 3 | 41

## ROI Toolkit Parameters (hidden)
ROI
FTE Cost
Quality Cost
Subscription Cost
Infra Cost
Other CAPEX
Other OPEX

## ROI-V1 (hidden)
Use Case Meta Data | [7 empty] | Existing Manual Monthly Cost | [5 empty] | FTE Saved/Day | BOT AHT (Min) | BOT FTE | FTE Cost | BOT Monthly Cost | [8 empty] | ROI
#Priority | UseCase | Already in Production | AverageTransactions(Annual) | OCR/NON-OCR | Frequency | Complexity | Manual AHT in Min /Transaction | Manual FTE Required/Day | FTE Cost (Per Day) | Seat Cost (Per Day) | Employee Cost (Others - Paid by ABG)* Per Day | Other OPEX Cost*Per Day | Total Cost (Per Day) |  |  |  |  | BOT FTE Required / Day | FTE Cost (Per Day) | Infra Cost (Per Day) | License Cost (Per Day) |  |  | Development & Support |  | Total Cost | ROI in Rupees (Per Day) | ROI In Percent
[21 empty] | Runner | Creater | Document Automation | Development | Support
NA | Data Change – Override Manager | Y | 6089 | NON-OCR | Daily | Medium | 3.8167 | 0.29794 | 476.7115 | 107.1111 | 52.4681 | 63.8793 | 700.1699 | 0.25325 | 2.2333 | 0.020921 | 1474.9432 | 0.044692 | 105.0255 | 166.6667 | 42.259 | 233.3333 | 0 | 2995.8678 | 289.8551 | 603.8062 | 96.3637 | 13.76%
NA | Data Change – Use Position Reports To | Y | 3933 | NON-OCR | Daily | Simple | 3.6167 | 0.18236 | 291.7815 | 65.5597 | 32.1142 | 39.0987 | 428.5541 | 0.15501 | 1.2333 | 0.0074626 | 526.1144 | 0.027355 | 64.2831 | 166.6667 | 15.0738 | 233.3333 | 0 | 1962.8099 | 289.8551 | 535.8787 | -107.3246 | -25.04%
NA | Job Architecture | Y | 10692 | NON-OCR | Daily | Medium | 3.1833 | 0.43636 | 698.1785 | 156.872 | 76.8433 | 93.5559 | 1025.4496 | 0.37091 | 0.81667 | 0.013434 | 947.0645 | 0.065454 | 153.8174 | 166.6667 | 27.1346 | 233.3333 | 0 | 2995.8678 | 289.8551 | 637.4738 | 387.9758 | 37.83%
NA | Ticket Creater | Y | 48701 | NON-OCR | Daily | Complex | 10 | 6.2437 | 9989.9487 | 2244.6166 | 1099.5187 | 1338.6531 | 14672.7372 | 3.7462 | 0.51667 | 0.038711 | 2729.1291 | 2.4975 | 5869.0949 | 166.6667 | 78.193 | 233.3333 | 0 | 3257.5758 | 289.8551 | 6403.8096 | 8268.9276 | 56.36%
NA | Talent Profile Creation BOT | Y | 5310 | NON-OCR | Based on requirement | Complex | 10 | 0.68077 | 1089.2308 | 244.7365 | 119.8835 | 145.9569 | 1599.8077 | 0.40846 | 0.28333 | 0.0023146 | 163.1804 | 0.27231 | 639.9231 | 166.6667 | 4.6753 | 233.3333 | 0 | 3257.5758 | 289.8551 | 1101.1201 | 498.6876 | 31.17%
NA | Poornata Status update - SR Update in Transaction | Y | 53182 | NON-OCR | Daily | Simple | 5 | 3.4091 | 5454.5641 | 1225.5724 | 600.343 | 730.9116 | 8011.391 | 2.7273 | 0.4 | 0.032727 | 2307.2806 | 0.68182 | 1602.2782 | 166.6667 | 66.1065 | 233.3333 | 0 | 2479.3388 | 289.8551 | 2124.9064 | 5886.4846 | 73.48%
NA | Audit Sampling | Y | 5000 | NON-OCR | Based on requirement | Simple | 10 | 0.64103 | 1025.641 | 230.4487 | 112.8846 | 137.4359 | 1506.4103 | 0.51282 | 0.4 | 0.0030769 | 216.9231 | 0.12821 | 301.2821 | 166.6667 | 6.2151 | 233.3333 | 0 | 2479.3388 | 289.8551 | 764.0189 | 742.3913 | 49.28%
NA | Cement ticket creator | Y | 5000 | NON-OCR | Daily | Complex | 10 | 0.64103 | 1025.641 | 230.4487 | 112.8846 | 137.4359 | 1506.4103 | 0.38462 | 0.78333 | 0.0060256 | 424.8077 | 0.25641 | 602.5641 | 166.6667 | 12.1713 | 233.3333 | 0 | 3257.5758 | 289.8551 | 1071.2571 | 435.1531 | 28.89%
NA | Potential Assesment | Y | 6316 | NON-OCR | Based on requirement | Medium | 10 | 0.80974 | 1295.5897 | 291.1028 | 142.5958 | 173.609 | 1902.8974 | 0.56682 | 8 | 0.077735 | 5480.3446 | 0.24292 | 570.8692 | 166.6667 | 157.0188 | 233.3333 | 0 | 2995.8678 | 289.8551 | 1184.4097 | 718.4877 | 37.76%
0 | Job Description Update | N | 7168 | NON-OCR | Daily | Complex | 10 | 0.91897 | 1470.359 | 330.3713 | 161.8314 | 197.0281 | 2159.5897 | 0.55138 | 8 | 0.088222 | 6219.6185 | 0.36759 | 863.8359 | 166.6667 | 178.1999 | 233.3333 | 0 | 2995.8678 | 289.8551 | 1498.5575 | 661.0322 | 30.61%
0 | FnF Settlement | N | 12829 | NON-OCR | Monthly | Complex | 10 | 1.6447 | 2631.5897 | 591.2853 | 289.6393 | 352.633 | 3865.1474 | 0.98685 | 8 | 0.1579 | 11131.6246 | 0.6579 | 1546.059 | 166.6667 | 318.9351 | 233.3333 | 0 | 2995.8678 | 289.8551 | 2321.5158 | 1543.6317 | 39.94%
1 | Initiate EJF Verification Process | N | 14999 | OCR | 0 | Complex | 30 | 5.7688 | 9230.1538 | 2073.9002 | 1015.8938 | 1236.8406 | 13556.7885 | 3.4613 | 8 | 0.1846 | 13014.5169 | 2.3075 | 5422.7154 | 166.6667 | 372.8823 | 233.3333 | 479.4521 | 4393.9394 | 289.8551 | 6731.5715 | 6825.217 | 50.35%
2 | Poornata ID Creation (Add a Person) (Proposed Process Change) | N | 8925 | OCR | Daily | Complex | 25 | 2.8606 | 4576.9231 | 1028.3774 | 503.7476 | 613.3077 | 6722.3558 | 1.7163 | 8 | 0.10985 | 7744.1538 | 1.1442 | 2688.9423 | 166.6667 | 221.8798 | 233.3333 | 479.4521 | 4393.9394 | 289.8551 | 3846.7959 | 2875.5599 | 42.78%
2 | Poornata ID creation (Through External Hire) – QC action and update if missing data-Proposed process change | N | 5854 | OCR | Daily | Complex | 25 | 1.8763 | 3002.0513 | 674.5234 | 330.4133 | 402.2749 | 4409.2628 | 1.1258 | 8 | 0.072049 | 5079.4708 | 0.75051 | 1763.7051 | 166.6667 | 145.5332 | 233.3333 | 479.4521 | 4393.9394 | 289.8551 | 2845.2122 | 1564.0507 | 35.47%
3 | Pratibha - OCR | N | 540 | OCR | Yearly | Complex | 120 | 0.83077 | 1329.2308 | 298.6615 | 146.2985 | 178.1169 | 1952.3077 | 0.49846 | 8 | 0.0066462 | 468.5538 | 0.33231 | 780.9231 | 166.6667 | 13.4247 | 233.3333 | 479.4521 | 4393.9394 | 289.8551 | 1730.3215 | 221.9862 | 11.37%
4 | AWOO(A world of opprtunity) - OCR | N | 2700 | OCR | Yearly | Complex | 120 | 4.1538 | 6646.1538 | 1493.3077 | 731.4923 | 890.5846 | 9761.5385 | 2.4923 | 8 | 0.033231 | 2342.7692 | 1.6615 | 3904.6154 | 166.6667 | 67.1233 | 233.3333 | 479.4521 | 4393.9394 | 289.8551 | 4907.7125 | 4853.826 | 49.72%
5 | Bank Data Update | N | 3695 | OCR | Weekly | Medium | 8 | 0.37897 | 606.359 | 136.2413 | 66.7374 | 81.2521 | 890.5897 | 0.26528 | 8 | 0.045477 | 3206.1231 | 0.11369 | 267.1769 | 166.6667 | 91.8595 | 233.3333 | 479.4521 | 3333.3333 | 289.8551 | 1295.0102 | -404.4204 | -45.41%
6 | Education Data | N | 2981 | OCR | Daily | Complex | 7 | 0.26753 | 428.041 | 96.1755 | 47.1113 | 57.3575 | 628.6853 | 0.16052 | 8 | 0.036689 | 2586.5908 | 0.10701 | 251.4741 | 166.6667 | 74.1091 | 233.3333 | 479.4521 | 4393.9394 | 289.8551 | 1261.557 | -632.8717 | -100.7%
6 | National ID, PAN, Aadhar, Passport, Visa, Address | N | 9845 | OCR | Weekly | Complex | 10 | 1.2622 | 2019.4872 | 453.7535 | 222.2698 | 270.6113 | 2966.1218 | 0.75731 | 8 | 0.12117 | 8542.4308 | 0.50487 | 1186.4487 | 166.6667 | 244.7514 | 233.3333 | 479.4521 | 4393.9394 | 289.8551 | 2367.1739 | 598.9479 | 20.19%
7 | Holiday Schedule upload | N | 10287 | NON-OCR | Monthly | Simple | 10 | 1.3188 | 2110.1538 | 474.1252 | 232.2488 | 282.7606 | 3099.2885 | 1.0551 | 8 | 0.12661 | 8925.9508 | 0.26377 | 619.8577 | 166.6667 | 255.7397 | 233.3333 | 479.4521 | 2479.3388 | 289.8551 | 1811.5712 | 1287.7172 | 41.55%
8 | Transfer of performance document | N | 3558 | NON-OCR | 0 | Medium | 10 | 0.45615 | 729.8462 | 163.9873 | 80.3287 | 97.7994 | 1071.9615 | 0.31931 | 8 | 0.043791 | 3087.2492 | 0.13685 | 321.5885 | 166.6667 | 88.4536 | 233.3333 | 479.4521 | 2995.8678 | 289.8551 | 1346.0158 | -274.0543 | -25.57%
9 | Job Data Update (Excel Input / Bulk Data Update) | N | 45835 | NON-OCR | Daily | Medium | 10 | 5.8763 | 9402.0513 | 2112.5234 | 1034.8133 | 1259.8749 | 13809.2628 | 4.1134 | 8 | 0.56412 | 39770.6769 | 1.7629 | 4142.7788 | 166.6667 | 1139.48 | 233.3333 | 479.4521 | 2995.8678 | 289.8551 | 6218.2326 | 7591.0302 | 54.97%
10 | Data Change – Data Change | N | 6804 | NON-OCR | Daily | Medium | 10 | 0.87231 | 1395.6923 | 313.5946 | 153.6134 | 187.0228 | 2049.9231 | 0.61062 | 8 | 0.083742 | 5903.7785 | 0.26169 | 614.9769 | 166.6667 | 169.1507 | 233.3333 | 479.4521 | 2995.8678 | 289.8551 | 1720.1014 | 329.8217 | 16.09%
Overall Program ROI | [7 empty] | 41.8284 |  |  |  |  | 98296.6506 |  |  |  |  | 14.589 | 34284.2354 | [6 empty] | 54328.0295 | 43968.6211 | 44.73%

## ROI-V2 (hidden)
Use Case Meta Data | [7 empty] | Existing Manual Monthly Cost | [5 empty] | FTE Saved/Month | BOT AHT | BOT FTE | FTE Cost | BOT Monthly Cost | [8 empty] | ROI
#Priority | UseCase | Already in Production | AverageTransactions(Annual) | OCR/NON-OCR | Frequency | Complexity | Manual AHT in Min /Transaction | Manual FTE Required/Month | FTE Cost | Seat Cost | Employee Cost (Others - Paid by ABG)* | Other OPEX Cost* | Total Cost |  |  |  |  | BOT FTE Required / Month | FTE Cost | Infra Cost | License Cost |  |  | Development & Support |  | Total Cost | ROI in Rupees | ROI In Percent
[21 empty] | Runner | Creater | Document Automation | Development | Support
NA | Data Change – Override Manager | Y | 6089 | NON-OCR | Daily | Medium | 3.8167 | 3.5753 | 171616.1231 | 38559.9977 | 18888.4995 | 22996.5605 | 252061.1808 | 3.039 | 2.2333 | 0.020921 | 1474.9432 | 0.5363 | 37809.1771 | 5000 | 23.1368 | 21000 | 0 | 197727.2727 | 22826.087 | 263385.6736 | -11324.4928 | -4.493%
NA | Data Change – Use Position Reports To | Y | 3933 | NON-OCR | Daily | Simple | 3.6167 | 2.1884 | 105041.3538 | 23601.4792 | 11561.114 | 14075.5414 | 154279.4885 | 1.8601 | 1.2333 | 0.0074626 | 526.1144 | 0.32825 | 23141.9233 | 5000 | 8.2529 | 21000 | 0 | 129545.4545 | 22826.087 | 180521.7177 | -26242.2292 | -17.01%
NA | Job Architecture | Y | 10692 | NON-OCR | Daily | Medium | 3.1833 | 5.2363 | 251344.2462 | 56473.9103 | 27663.5761 | 33680.129 | 369161.8615 | 4.4509 | 0.81667 | 0.013434 | 947.0645 | 0.78545 | 55374.2792 | 5000 | 14.8562 | 21000 | 0 | 197727.2727 | 22826.087 | 280942.4951 | 88219.3664 | 23.9%
NA | Ticket Creater | Y | 48701 | NON-OCR | Daily | Complex | 10 | 74.9246 | 3596381.5385 | 808061.9769 | 395826.7431 | 481915.1262 | 5282185.3846 | 44.9548 | 0.51667 | 0.038711 | 2729.1291 | 29.9698 | 2112874.1538 | 5000 | 42.8107 | 21000 | 0 | 215000 | 22826.087 | 2355743.0515 | 2926442.3332 | 55.4%
NA | Talent Profile Creation BOT | Y | 5310 | NON-OCR | Based on requirement | Complex | 10 | 8.1692 | 392123.0769 | 88105.1538 | 43158.0462 | 52544.4923 | 575930.7692 | 4.9015 | 0.28333 | 0.0023146 | 163.1804 | 3.2677 | 230372.3077 | 5000 | 2.5597 | 21000 | 0 | 215000 | 22826.087 | 473200.9544 | 102729.8148 | 17.84%
NA | Poornata Status update - SR Update in Transaction | Y | 53182 | NON-OCR | Daily | Simple | 5 | 40.9092 | 1963643.0769 | 441206.0538 | 216123.4662 | 263128.1723 | 2884100.7692 | 32.7274 | 0.4 | 0.032727 | 2307.2806 | 8.1818 | 576820.1538 | 5000 | 36.1933 | 21000 | 0 | 163636.3636 | 22826.087 | 768318.7977 | 2115781.9715 | 73.36%
NA | Audit Sampling | Y | 5000 | NON-OCR | Based on requirement | Simple | 10 | 7.6923 | 369230.7692 | 82961.5385 | 40638.4615 | 49476.9231 | 542307.6923 | 6.1538 | 0.4 | 0.0030769 | 216.9231 | 1.5385 | 108461.5385 | 5000 | 340.2778 | 21000 | 0 | 163636.3636 | 22826.087 | 300264.2668 | 242043.4255 | 44.63%
NA | Cement ticket creator | Y | 5000 | NON-OCR | Daily | Complex | 10 | 7.6923 | 369230.7692 | 82961.5385 | 40638.4615 | 49476.9231 | 542307.6923 | 4.6154 | 0.78333 | 0.0060256 | 424.8077 | 3.0769 | 216923.0769 | 5000 | 6.6638 | 21000 | 0 | 215000 | 22826.087 | 459755.8277 | 82551.8647 | 15.22%
NA | Potential Assesment | Y | 6316 | NON-OCR | Based on requirement | Medium | 10 | 9.7169 | 466412.3077 | 104797.0154 | 51334.5046 | 62499.2492 | 685043.0769 | 6.8018 | 8 | 0.077735 | 5480.3446 | 2.9151 | 205512.9231 | 5000 | 85.9678 | 21000 | 0 | 197727.2727 | 22826.087 | 431152.2505 | 253890.8264 | 37.06%
0 | Job Description Update | N | 7168 | NON-OCR | Daily | Complex | 10 | 11.0277 | 529329.2308 | 118933.6615 | 58259.2985 | 70930.1169 | 777452.3077 | 6.6166 | 8 | 0.088222 | 6219.6185 | 4.4111 | 310980.9231 | 5000 | 97.5644 | 21000 | 0 | 197727.2727 | 22826.087 | 536631.8472 | 240820.4605 | 30.98%
0 | FnF Settlement | N | 12829 | NON-OCR | Monthly | Complex | 10 | 19.7369 | 947372.3077 | 212862.7154 | 104270.1646 | 126947.8892 | 1391453.0769 | 11.8422 | 8 | 0.1579 | 11131.6246 | 7.8948 | 556581.2308 | 5000 | 174.6169 | 21000 | 0 | 197727.2727 | 22826.087 | 782309.2074 | 609143.8695 | 43.78%
1 | Initiate EJF Verification Process | N | 14999 | OCR | 0 | Complex | 30 | 69.2262 | 3322855.3846 | 746604.0692 | 365721.7708 | 445262.6215 | 4880443.8462 | 41.5357 | 8 | 0.1846 | 13014.5169 | 27.6905 | 1952177.5385 | 5000 | 204.1531 | 21000 | 14583.3333 | 290000 | 22826.087 | 2284791.1118 | 2595652.7343 | 53.18%
2 | Poornata ID Creation (Add a Person) (Proposed Process Change) | N | 8925 | OCR | Daily | Complex | 25 | 34.3269 | 1647692.3077 | 370215.8654 | 181349.1346 | 220790.7692 | 2420048.0769 | 20.5962 | 8 | 0.10985 | 7744.1538 | 13.7308 | 968019.2308 | 5000 | 121.4792 | 21000 | 14583.3333 | 290000 | 22826.087 | 1300550.1302 | 1119497.9467 | 46.26%
2 | Poornata ID creation (Through External Hire) – QC action and update if missing data-Proposed process change | N | 5854 | OCR | Daily | Complex | 25 | 22.5154 | 1080738.4615 | 242828.4231 | 118948.7769 | 144818.9538 | 1587334.6154 | 13.5092 | 8 | 0.072049 | 5079.4708 | 9.0062 | 634933.8462 | 5000 | 79.6794 | 21000 | 14583.3333 | 290000 | 22826.087 | 967422.9459 | 619911.6695 | 39.05%
3 | Pratibha - OCR | N | 540 | OCR | Yearly | Complex | 120 | 9.9692 | 478523.0769 | 107518.1538 | 52667.4462 | 64122.0923 | 702830.7692 | 5.9815 | 8 | 0.0066462 | 468.5538 | 3.9877 | 281132.3077 | 5000 | 7.35 | 21000 | 14583.3333 | 290000 | 22826.087 | 613549.078 | 89281.6912 | 12.7%
4 | AWOO(A world of opprtunity) - OCR | N | 2700 | OCR | Yearly | Complex | 120 | 49.8462 | 2392615.3846 | 537590.7692 | 263337.2308 | 320610.4615 | 3514153.8462 | 29.9077 | 8 | 0.033231 | 2342.7692 | 19.9385 | 1405661.5385 | 5000 | 36.75 | 21000 | 14583.3333 | 290000 | 22826.087 | 1738107.7088 | 1776046.1374 | 50.54%
5 | Bank Data Update | N | 3695 | OCR | Weekly | Medium | 8 | 4.5477 | 218289.2308 | 49046.8615 | 24025.4585 | 29250.7569 | 320612.3077 | 3.1834 | 8 | 0.045477 | 3206.1231 | 1.3643 | 96183.6923 | 5000 | 50.2931 | 21000 | 14583.3333 | 220000 | 22826.087 | 358643.4057 | -38031.098 | -11.86%
6 | Education Data | N | 2981 | OCR | Daily | Complex | 7 | 3.2103 | 154094.7692 | 34623.1685 | 16960.0555 | 20648.6991 | 226326.6923 | 1.9262 | 8 | 0.036689 | 2586.5908 | 1.2841 | 90530.6769 | 5000 | 40.5747 | 21000 | 14583.3333 | 290000 | 22826.087 | 422980.6719 | -196653.9796 | -86.89%
6 | National ID, PAN, Aadhar, Passport, Visa, Address | N | 9845 | OCR | Weekly | Complex | 10 | 15.1462 | 727015.3846 | 163351.2692 | 80017.1308 | 97420.0615 | 1067803.8462 | 9.0877 | 8 | 0.12117 | 8542.4308 | 6.0585 | 427121.5385 | 5000 | 134.0014 | 21000 | 14583.3333 | 290000 | 22826.087 | 759664.9601 | 308138.886 | 28.86%
7 | Holiday Schedule upload | N | 10287 | NON-OCR | Monthly | Simple | 10 | 15.8262 | 759655.3846 | 170685.0692 | 83609.5708 | 101793.8215 | 1115743.8462 | 12.6609 | 8 | 0.12661 | 8925.9508 | 3.1652 | 223148.7692 | 5000 | 140.0175 | 21000 | 0 | 163636.3636 | 22826.087 | 414751.2373 | 700992.6088 | 62.83%
8 | Transfer of performance document | N | 3558 | NON-OCR | 0 | Medium | 10 | 5.4738 | 262744.6154 | 59035.4308 | 28918.3292 | 35207.7785 | 385906.1538 | 3.8317 | 8 | 0.043791 | 3087.2492 | 1.6422 | 115771.8462 | 5001 | 48.4283 | 21000 | 0 | 197727.2727 | 22826.087 | 341374.6342 | 44531.5197 | 11.54%
9 | Job Data Update (Excel Input / Bulk Data Update) | N | 45835 | NON-OCR | Daily | Medium | 10 | 70.5154 | 3384738.4615 | 760508.4231 | 372532.7769 | 453554.9538 | 4971334.6154 | 49.3608 | 8 | 0.56412 | 39770.6769 | 21.1546 | 1491400.3846 | 5000 | 623.8653 | 21000 | 0 | 197727.2727 | 22826.087 | 1717577.6096 | 3253757.0058 | 65.45%
10 | Data Change – Data Change | N | 6804 | NON-OCR | Daily | Medium | 10 | 10.4677 | 502449.2308 | 112894.0615 | 55300.8185 | 67328.1969 | 737972.3077 | 7.3274 | 8 | 0.083742 | 5903.7785 | 3.1403 | 221391.6923 | 5000 | 92.61 | 21000 | 0 | 197727.2727 | 22826.087 | 447037.662 | 290934.6457 | 39.42%
[8 empty] | 501.9403 | 24093136.4923 | 5413426.6056 | 2651750.8352 | 3228480.29 | 35386794.2231 | 326.8719 |  |  |  | 175.0684
Overall Program ROI | [12 empty] | 70773588.4462 | [12 empty] | 18198677.2451 | 52574911.2011 | 74.29%

## Configurations (hidden)
Parameter | Value
Days Per Year | 200
Days Per Month | 16.6667
Infra Cost | 5000
Working Hours Per day | 6.5
Mins Per Hour | 60
FTE Saved Simple | 80%
FTE Saved Medium | 70%
FTE Saved Complex | 60%

## Runner Cost Verification (hidden)
Runner License Verification |  |  | Annual Transaction | AHT Per transaction | Total Annual Mins | Total Annual HR | Total Monthly HR | FTE Required
Transactions per year | 6089 | 6089 | 6089 | 3.82 | 23259.98 | 387.6663 | 23.26 | 3.5785
Days per year | 200 | 200 | 3933 | 3.62 | 14237.46 | 237.291 | 14.2375 | 2.1904
Transaction Per Month | 507.4167 | 30.445 | 10692 | 3.18 | 34000.56 | 566.676 | 34.0006 | 5.2309
AHT per transaction (mins) | 0.0223 |  | 48701 | 10 | 487010 | 8116.8333 | 487.01 | 74.9246
Runner license cost per month (INR) | 49000 |  | 5310 | 10 | 53100 | 885 | 53.1 | 8.1692
Runner license cost per day (INR) | 2940 |  | 53182 | 5 | 265910 | 4431.8333 | 265.91 | 40.9092
Minutes per day | 1440 |  | 5000 | 10 | 50000 | 833.3333 | 50 | 7.6923
Runner license cost per minute (INR) | 2.0417 |  | 5000 | 10 | 50000 | 833.3333 | 50 | 7.6923
Time required for BOT | 11.3154 |  | 6316 | 10 | 63160 | 1052.6667 | 63.16 | 9.7169
Total cost | 23.1023 |  | 7168 | 10 | 71680 | 1194.6667 | 71.68 | 11.0277
|  |  | 12829 | 10 | 128290 | 2138.1667 | 128.29 | 19.7369
|  |  | 14999 | 30 | 449970 | 7499.5 | 449.97 | 69.2262
|  |  | 8925 | 25 | 223125 | 3718.75 | 223.125 | 34.3269
|  |  | 5854 | 25 | 146350 | 2439.1667 | 146.35 | 22.5154
|  |  | 540 | 120 | 64800 | 1080 | 64.8 | 9.9692
|  |  | 2700 | 120 | 324000 | 5400 | 324 | 49.8462
|  |  | 3695 | 8 | 29560 | 492.6667 | 29.56 | 4.5477
|  |  | 2981 | 7 | 20867 | 347.7833 | 20.867 | 3.2103
|  |  | 9845 | 10 | 98450 | 1640.8333 | 98.45 | 15.1462
|  |  | 10287 | 10 | 102870 | 1714.5 | 102.87 | 15.8262
|  |  | 3558 | 10 | 35580 | 593 | 35.58 | 5.4738
|  |  | 45835 | 10 | 458350 | 7639.1667 | 458.35 | 70.5154
|  |  | 6804 | 10 | 68040 | 1134 | 68.04 | 10.4677
|  |  |  | Total Hours Annual | 54376.8333
|  |  |  | Total Hours /Month | 3262.61
|  |  |  | FTE Required | 501.94 |  |  | 501.94
35386770

## Assumptions
Assumptions | Value
Working Days in a Year | 200
Working Days per Month | 22
Working Hours per Day | 6.5
BOT Accuracy - Complex | 70%
BOT Accuracy - Medium | 80%
BOT Accuracy - Simple | 90%
Monthly VM Cost | 57.7901
Mins Per Hour | 60
Monthly FTE Cost | 554.785
Monthly Paid Days for FTE | 30
Monthly Seat Cost | 124.6533
Monthly FTEOther Cost | 61.061
Monthly Other OPEX | 74.3412
Number of VM's | 5
Number of Processes | 23
BOT Days in a Year | 365
BOT Number of Days Per Month | 30
BOT Number of Hours in a Day | 24
Monthly Runner License Cost | 566.343
Document Automation Cost | 16181.2298
Monthly Creater License Cost | 242.7184
Creater License Average Out Time | 3
Number Of Documents per OCR License | 50000
Developer Cost Per Resource | 1733.7032
Support Cost Per resource | 1155.8021

## Estimation Guidelines
Type | Complexity | Concat | Requirement Gathering & PDD | SDD | Development | QA | UAT | Production Deployment | Hypercare | Total Man Days | Total Efforts(Weeks)
OCR | Simple | OCRSimple | 2 | 2 | 10 | 3 | 2 | 2 | 10 | 31 | 6.2
OCR | Medium | OCRMedium | 3 | 2 | 20 | 4 | 3 | 2 | 10 | 44 | 8.8
OCR | Complex | OCRComplex | 4 | 2 | 30 | 5 | 5 | 2 | 10 | 58 | 11.6
NON-OCR | Simple | NON-OCRSimple | 2 | 1 | 8 | 1 | 1 | 1 | 10 | 24 | 4.8
NON-OCR | Medium | NON-OCRMedium | 2 | 1 | 10 | 3 | 2 | 1 | 10 | 29 | 5.8
NON-OCR | Complex | NON-OCRComplex | 2 | 2 | 20 | 5 | 3 | 1 | 10 | 43 | 8.6
* Above estimatesion is based on 2 Developers 1 BA 1 QA 1 PM